## ENROUTE SITE
CLIENT PO | CARGO DETAILS | CLIENT | KAMOA PO NUMBER | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | VESSEL DETAILS & ETA | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU ARR | CHIRUNDU DISP | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKEY ARR | WHISKEY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 20-03-2026 | COMMENTS 23-03-2026 | COMMENTS 24-03-2026 | COMMENTS 25-03-2026 | COMMENTS 26-03-2026 | COMMENTS 27-03-2026 | COMMENTS 30-03-2026 | COMMENTS 31-03-2026 | COMMENTS 01-04-2026 | COMMENTS 02-04-2026 | COMMENTS 08-04-2026 | COMMENTS 09-04-2026 | COMMENTS 10-04-2026 | COMMENTS 10-04-2026 | COMMENTS 14-04-2026 | COMMENTS 15-04-2026 | COMMENTS 16-04-2026 | COMMENTS 20-04-2026 | COMMENTS 21-04-2026 | COMMENTS 22-04-2026 | COMMENTS 23-04-2026 | COMMENTS 24-04-2026 | COMMENTS 27-04-2026 | COMMENTS 28-04-2026 | COMMENTS 29-04-2026 | COMMENTS 30-04-2026 | COMMENTS 04-05-2026 | COMMENTS 05-05-2026 | COMMENTS 06-05-2026 | COMMENTS 07-05-2026 | COMMENTS 08-05-2026 | COMMENTS 11-05-2026 | COMMENTS 12-05-2026 | COMMENTS 13-05-2026 | COMMENTS 14-05-2026 | COMMENTS 15-05-2026 | COMMENTS 18-05-2026 | COMMENTS 18-05-2026 | COMMENTS 20-05-2026 | COMMENTS 21-05-2026 | COMMENTS 22-05-2026 | COMMENTS 25-05-2026 | COMMENTS 26-05-2026 | COMMENTS 27-05-2026 | COMMENTS 28-05-2026 | COMMENTS 29-05-2026 | COMMENTS 01-06-2026 | COMMENTS 02-06-2026 | COMMENTS 03-06-2026 | COMMENTS 04-06-2026 | COMMENTS 05-06-2026 | COMMENTS 08-06-2026 | COMMENTS 09-06-2026 | COMMENTS 10-06-2026 | COMMENTS 11-06-2026 | COMMENTS 12-06-2026 | COMMENTS 15-06-2026
BA2951 | EG20 TIER 3 MINING GRADER | BARTRAC EQUIPMENT - KAMOA COPPER | PO55702OX | 21NK0113 | CAT00120VE9601161 | E7A67192 | 2603DSI2788 | VESSEL: ARIES Voy. 611N - Transhipment Vessel: CMA CGM OHIO Voy. 615S - ETA DURBAN PORT: 11-05-2026 | COD 2025 341452 | BCF2053ZM | BCF2676ZM | 2603DSI2788 | KASUMBALESA - UNDER CLEARANCE | 10-12-2025 | 13-05-2026 | 20-05-2026 | CRF ISSUE DATE 20-05-2026 | 11-05-2026 | 19-05-2026 | 20-05-2026 | 21-05-2026 | 21-05-2026 | GRB 22-05-2026 | MARTINS DRIFT 25-05-2026 | FRANCISTOWN 30-05-2026 | KAZUNGULA BW 30-05-2026 | 2026-06-05 | 2026-06-08 | 2026-06-08 | [9 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 10-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 10-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 10-05-2026 | VESSEL DUE TO ARRIVE TODAY | VESSEL DUE TO ARRIVE TODAY | VESSEL DUE TO ARRIVE TODAY | LOADING TOMORROW | LOADING TODAY | LOADING WAS DELAYED - LOADING TODAY | DISPATCHING DURBAN FOR GROBLRESBRIDGE BORDER | ENROUTE GROBLERS BRIDGE BORDER | FRANKFORT ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | MARTINS DRIFT BORDER TO DISPATCH | MARTINS DRIFT BORDER TO DISPATCH ONCE RELEASED | DISPATCHING MARTINS DRIFT FOR KAZUNGULA BORDER | DRIVER DID NOT DISPATCH YESTERDAY - DELAYED WITH FUEL - TO DISPACH ONCE REFUELED | MARTINS DRIFT BORDER AWAITING FUEL - DELAYED WITH FUEL - TO DISPACH ONCE REFUELED | KAZUNGULA - UNDER CLEARANCE | KAZUNGULA - UNDER CLEARANCE - DAY 2 | KAZUNGULA - DISPATCHING | KAZUNGULA - DISPATCHING TO ZAMBIAN SIDE | KAZUNGULA - IN QUEUE TO ZAMBIAN SIDE | NDOLA - BUSY WITH ROUTINE MAINTENANCE CHECKS ON VEHICLE BEFORE DISPATCHING FOR KASUMBALESA BORDER | NDOLA - BUSY WITH ROUTINE MAINTENANCE CHECKS ON VEHICLE BEFORE DISPATCHING FOR KASUMBALESA BORDER | NDOLA - DISPATCHING | KASUMBALESA - UNDER CLEARANCE | KASUMBALESA - UNDER CLEARANCE | KASUMBALESA - UNDER CLEARANCE

## OFFLOADED - 2026
CLIENT PO | CARGO DETAILS | CLIENT | KAMOA PO NUMBER | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU ARR | CHIRUNDU DISP | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKEY ARR | WHISKEY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 11-12-2025 | COMMENTS 12-12-2025 | COMMENTS 15-12-2025 | COMMENTS 17-12-2025 | COMMENTS 18-12-2025 | COMMENTS 19-12-2025 | COMMENTS 22-12-2025 | COMMENTS 23-12-2025 | COMMENTS 24-12-2025 | COMMENTS 29-12-2025 | COMMENTS 30-12-2025 | COMMENTS 31-12-2025 | COMMENTS 02-01-2026 | COMMENTS 05-01-2026 | COMMENTS 06-01-2026 | COMMENTS 07-01-2026 | COMMENTS 08-01-2026 | COMMENTS 09-01-2026 | COMMENTS 12-01-2026 | COMMENTS 13-01-2026 | COMMENTS 14-01-2026 | COMMENTS 15-01-2026 | COMMENTS 16-01-2026 | COMMENTS 19-01-2026 | COMMENTS 20-01-2026 | COMMENTS 21-01-2026 | COMMENTS 22-01-2026 | COMMENTS 23-01-2026 | COMMENTS 26-01-2026 | COMMENTS 27-01-2026 | COMMENTS 28-01-2026 | COMMENTS 29-01-2026 | COMMENTS 02-02-2026 | COMMENTS 03-02-2026
BA2949 | EG20-T3 MINING GRADER | BARTRAC EQUIPMENT - KAMOA COPPER | OX-55702 | 21MK0109 | CAT00120LE9601132 | E7A66137 | FML2512DSI2741 | COD 2025 341452 | BCG8261ZM | BCH2148ZM | 2512DSI2741 | VESSEL: WESTPORT Voy. TBA Transhipment Vessel: CMA CGM RIO GRANDE Voy. 548S - ETA DURBAN: 29-12-2025 | OFFLOADED - 30-01-2026 | 10-12-2025 | 05-01-2026 | 06-01-2026 | CRF ISSUE DATE 06-01-2026 | 29-12-2025 | 08-01-2026 | 08-01-2026 | 09-01-2026 | MOKOPANE 09-01-2026 | GRB 10-01-2026 | GRB 12-01-2026 | FRANCISTOWN 12-01-2026 | KAZUNGULA 12-01-2026 | KAZUNGULA 14-01-2026 | 15-01-2026 | 2026-01-16 | 17-01-2026 | 2026-01-20 | 22-01-2026 | 23-01-2026 | 2026-01-27 | 27-01-2026 | 27-01-2026 | 2026-01-28 | 2026-01-30 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-12-2025 | VESSEL DUE TO ARRIVE TODAY 29-12-2025 | VESSEL IN AND WORKING | VESSEL STILL DISCHARGING CONTAINERS | CONTAINER COLLECTED FORM PORT - TO BE UNPACKED TODAY. BV INSPECTION TO BE BOOKED FOR MONDAY 05-01-2026 | BV INSPECTION BOOKED FOR TODAY 05-01-2026 | LOADING TODAY | VEHICLE DELAYED - ENROUTE TO WAREHOUSE - LOADING TODAY | LOADED TO DISPATCH DURBAN TODAY | MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | GROBLERSBRIDGE BORDER CLEARING AND WAITING RELEASE | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KALOMO EN-ROUTE LUSAKA | KABWE ENROUTE KASUMBALESA BORDER | KONKOLA ENROUTE KASUMBALESA BORDER | KONKOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER CLEARNING | KASUMBALESA BORDER CLEARNING | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 5 | DSP WHISKEY EN ROUTE KOLWEZI | LUAMBO EN ROUTE KOLWEZI | KAMOA - WAITING TO OFFLOAD | OFFLOADED - 30-01-2026 | OFFLOADED - 30-01-2026
BA2950 | EG20 TIER 3 MINING GRADER | BARTRAC EQUIPMENT - KAMOA COPPER | PO55702OX | 21NK0112 | CAT00120CE9601160 | E7A67305 | 2602DSI2783 | VESSEL: ONE COSMOS Voy. 608N - Transhipment Vessel: TRANCURA Voy. 612S - ETA DURBAN: 20-04-2026 | COD 2025 341452 PT02 | CAK4790ZM | CAK6059ZM | 2602DSI2783 | OFFLOADED 21-05-2026 | 10-12-2025 | 23-04-2026 | 30-04-2026 | CRF ISSUE DATE 30-04-2026 | 19-04-2026 | 24-04-2026 | 25-04-2026 | 27-04-2026 | ZEERUST 28-04-2026 | KOPFONTEIN BORDER 29-04-2026 | KOPFONTEIN BORDER 30-04-2026 | GABORONE 30-04-2026 | 2026-05-01 | 2026-05-02 | 2026-04-04 | 2026-04-04 | 2026-05-05 | 2026-05-06 | 2026-05-09 | 2026-05-09 | 2026-05-13 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 21-05-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2026 |  | VESSEL IN AND WORKING | VESSEL IN AND WORKING - WAITING TO COLLECT THE CONTAINER FOR UNPACK | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION PLANNED FOR TOMORROW 23-04-2026 | BV INSPECTION BOOKED FOR TODAY 23-04-2026 | LOADING TODAY | LOADING TODAY | LOADING TODAY | KOPFONTEIN BORDER RSA SIDE CLEARING | GABORONE ENROUTE KAZUNGULA BORDER | DISPATCHED CHIRUNDU BORDER ENROUTE LUSAKA | KITWE | KASUMBALESA - WAITING TO CROSS | KASUMBALESA - WAITING TO CROSS - DAY 2 | KASUMBALESA - WAITING TO CROSS - DAY 3 | WHISKEY - UNDER CLEARANCE | WHISKEY - UNDER CLEARANCE - DAY 2 | WHISKEY - UNDER CLEARANCE - DAY 3 | WHISKEY - DISPATCHING | LUBUMBASHI | CONNEX KOLWEZI - CLEARING | WAITING TO OFFLOAD | WAITING TO OFFLOAD - DAY 2 | WAITING TO OFFLOAD - DAY 4 | OFFLOADED 21-05-2026

## OFFLOADED - 2025
CLIENT PO | CARGO DETAILS | CLIENT | KAMOA PO NUMBER | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU ARR | CHIRUNDU DISP | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKEY ARR | WHISKEY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 14-11-2024 | COMMENTS 15-11-2024 | COMMENTS 18-11-2024 | COMMENTS 19-11-2024 | COMMENTS 20-11-2024 | COMMENTS 21-11-2024 | COMMENTS 22-11-2024 | COMMENTS 25-11-2024 | COMMENTS 26-11-2024 | COMMENTS 27-11-2024 | COMMENTS 28-11-2024 | COMMENTS 29-11-2024 | COMMENTS 02-12-2024 | COMMENTS 03-12-2024 | COMMENTS 04-12-2024 | COMMENTS 05-12-2024 | COMMENTS 06-12-2024 | COMMENTS 09-12-2024 | COMMENTS 10-12-2024 | COMMENTS 11-12-2024 | COMMENTS 12-12-2024 | COMMENTS 13-12-2024 | COMMENTS 16-12-2024 | COMMENTS 17-12-2024 | COMMENTS 18-12-2024 | COMMENTS 19-12-2024 | COMMENTS 20-12-2024 | COMMENTS 23-12-2024 | COMMENTS 24-12-2024 | COMMENTS 27-12-2024 | COMMENTS 30-12-2024 | COMMENTS 02-01-2025 | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 13-01-2025 | COMMENTS 14-01-2025 | COMMENTS 15-01-2025 | COMMENTS 16-01-2025
BA2822 | CAT966GC-01B WHEEL LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 53498 OX | SGW02698 | CAT00966CSGW02698 | NTB14737 | FML2410DSI2616 | COD 2024 332314 | BZ72VLZN | ND184465 | ND61092 | VESSEL: MORNING CARINA Voy. 161 - ETA DURBAN: 07-12-2024 | OFFLOADED 15-01-2025 | 15-11-2024 | 11-12-2024 |  | BV COMPLETED | 07-12-2024 | 12-12-2024 | 12-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 24-12-2024 | 24-12-2024 | 25-12-2024 | 26-12-2024 | 26-12-2024 | 27-12-2024 | 29-12-2024 | 31-12-2024 | 06-01-2025 | 06-01-2025 | 10-01-2025 | 10-01-2025 | 11-01-2025 | 12-01-2025 | 15-01-2025 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 06-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 07-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 07-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 07-12-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 07-12-2024 | VESSEL ARRIVED 07-12-2024 - CURRENTLY DISCHARGING CARGO | UNIT COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 11-12-2024 | BV INSPECTION BOOKED FOR TODAY | FRERE ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER ON TUESDAY - DUE TO ROAD EMBARGO FOR THE LONG WEEKEND | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER ON TUESDAY - DUE TO ROAD EMBARGO FOR THE LONG WEEKEND | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE BORDER | BOKSBURG ENROUTE BEIT BRIDGE BORDER | PIENAARS REVIER ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE TO DISPATCH FOR HARARE | MASVINGO ENROUTE HARARE | KABWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE | KASUMBALESA ZAMBIAN SIDE AWAITING RELEASE | KASUMBALESA DRC SIDE AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | DISPATCHING WHISKEY TODAY | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 15-01-2025
BA2829 | CAT CS16 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 53676 OX | 57N00122 | CAT0CS16A57N00122 | E7A64491 | FML2412DSI2638 | COD 2024 365417 | BL64MKZN | ND702944 | ND59408 | VESSEL: TOREADOR Voy. 034 - ETA DURBAN: 14-01-2025 | OFFLOADED 13-02-2025 | 30-12-2024 | 17-01-2025 |  | BV COMPLETED | 14-10-2025 | 20-01-2025 | 20-01-2025 | 21-01-2025 | 21-01-2025 | 21-01-2025 | 25-01-2025 | 26-01-2025 | 28-01-2025 | 29-01-2025 | 30-01-2025 | 30-01-2025 | 31-01-2025 | 31-01-2025 | 01-02-2025 | 01-02-2025 | 06-02-2025 | 07-02-2025 | 08-02-2025 | 08-02-2025 | 13-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2025 | VESSEL IN AND WORKING | COLLECTING UNIT FROM PORT TODAY | UNIT COLLECTED FROM PORT - BV INSPECTION TO BE DONE PM TODAY | BV INSPECTION COMPLETED - DISPATCHING DURBAN TODAY | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | BEIT BRIDGE RSA BORDER CLEARING | BEIT BRIDGE RSA BORDER CLEARING AND WAITING FOR ZIM NOTIFICATION | BEIT BRIDGE ZIM SIDE CLEARING | HARARE ENROUTE CHIRUNDU BORDER | MAKUTI ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAMBIAN SIDE CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 - PLEASE ASSIST | WHISKEY AWAITING RELEASE - DAY 4 - PLEASE ASSIST | KANYAKA AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 13-02-2025
BA2845 | CAT CS16 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 53577 OX | 57N00126 | CAT0CS16C57N00126 | E7A64579 | FML2412DSI2650 | COD 2025 113347 | BP43GGZN | BJ85MZZN | ND59435 | VESSEL: TARIFA Voy. 146 - ETA DURBAN: 05-02-2025 | OFFLOADED 06-03-2025 | 23-01-2025 | 10-02-2025 |  | BV COMPLETED | 06-02-2025 | 12-02-2025 | 12-02-2025 | 12-02-2025 | 12-02-2025 | 13-02-2025 | 15-02-2025 | 16-02-2025 | 17-02-2025 | 19-02-2025 | 19-02-2025 | 20-02-2025 | 20-02-2025 | 20-02-2025 | 26-02-2025 | 26-02-2025 | 02-03-2025 | 02-03-2025 | 03-03-2025 | 04-03-2025 | 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | VESSEL IN AND WORKING | COLLECTING UNIT FROM PORT TODAY | BV INSPECTION BOOKED FOR TODAY 10-02-2025 | DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER ZIM SIDE CLEARING | DISPATCHING CHIRUNDU BORDER | KABWE ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA BORDER ZAM SIDE CLEARING | KASUMBALESA BORDER DRC SIDE AWAITING RELEASER TO PROCEED TO WHISKEY (TR8 NOT YET FINALIZE) | KASUMBALESA BORDER DRC SIDE AWAITING RELEASER TO PROCEED TO WHISKEY (TR8 NOT YET FINALIZE) | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | LUBUMBASHI ENROUTE KOLWEZI | KOLWEZI TO PROCEED TO SITE | KAMOA BOND STORE - DOCS BEING PROCESSED - AWAITING RELEASE FOR OFFLOADING | KAMOA BOND STORE - DOCS BEING PROCESSED - AWAITING RELEASE FOR OFFLOADING | OFFLOADED 06-03-2025
BA2843 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | 01013-OX-54040 | DXZ04144 | CAT0226BHDXZ04144 | CZ213326 | FML2501DSI2660 | COD 2025 122669 | HL40KXGP | N/A | 2501DSI2660 | VESSEL: APL BOSTON - TRANSHIPMENT VESSEL: MSC FIE X Voy. ZF452R - ETA DURBAN: 10-02-2025 | OFFLOADED 22-03-2025 | 13-02-2025 | 17-02-2025 |  | BV COMPLETED | 10-02-2025 | 05-03-2025 | 05-03-2025 | 06-03-2025 | RUSTENBURG 07-03-2025 | SKILPADHEK 07-03-2025 | SKILPADHEK 08-03-2025 | FRANCISTOWN 09-03-2025 | KAZUNGULA 09-03-2025 | KAZUNGULA DISP 12-03-2025 | 13-03-2025 | 15-03-2025 | 17-06-2025 | SAKANIA 17-06-2025 | SAKANIA 18-03-2025 | KANYAKA 19-03-2025 | KANYAKA 19-03-2025 | 19-03-2025 | 19-03-2025 | 19-03-2025 | 22-03-2025 | [18 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | VESSEL DUE TO ARRIVE TODAY 10-02-2025 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTION FROM PORT TODAY | BV INSEPCTION TO BE DONE TODAY - LOADING WEDNESDAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR TOMORROW | LOADING PLANNED FOR FRIDAY | VEHICLE DELAYED NEW LOADING PLANNED - MONDAY 24-02-2025 | VEHICLE DELAYED NEW LOADING PLANNED - MONDAY 24-02-2025 | LOADING TODAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED LOADING THURSDAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED LOADING THURSDAY / FRIDAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED LOADING THURSDAY / FRIDAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED TO LOAD NEXT WEEK | LOADING TODAY | LOADED TO DISPATCH DURBAN TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | DISPATCHED DURBAN ENROUTE JOHANNESBURG | ENROUTE SKILPADHEK BORDER | KAZUNGULA BOTSWANA SIDE CLEARING | KAZUNGULA BOTSWANA SIDE IN THE QUEUE TO CROSS TO ZAMBIAN SIDE | LIVINGSTONE ENROUTE SAKANIA BORDER | LUSAKA | DISPATCHING LUSAKA FOR SAKANIA BORDER | NDOLA - DISPATCHING FOR SAKANIA BORDER | SAKANIA DRC SIDE | KANYAKA AWAITING RELEASE | KAMOA BONDED TRUCK PARK | OFFLOADED 22-03-2025
BA2844 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | 53538 OX | DXZ04143 | CAT0226BLDXZ04143 | CZ213320 | FML2501DSI2660 | COD 2025 120623 | HL40KXGP | N/A | 2501DSI2660 | VESSEL: APL BOSTON - TRANSHIPMENT VESSEL: MSC FIE X Voy. ZF452R - ETA DURBAN: 10-02-2025 | OFFLOADED 22-03-2025 | 31-01-2025 | 17-02-2025 |  | BV COMPLETED | 10-02-2025 | 05-03-2025 | 05-03-2025 | 06-03-2025 | RUSTENBURG 07-03-2025 | SKILPADHEK 07-03-2025 | SKILPADHEK 08-03-2025 | FRANCISTOWN 09-03-2025 | KAZUNGULA 09-03-2025 | KAZUNGULA DISP 12-03-2025 | 13-03-2025 | 15-03-2025 | 17-06-2025 | SAKANIA 17-06-2025 | SAKANIA 18-03-2025 | KANYAKA 19-03-2025 | KANYAKA 19-03-2025 | 19-03-2025 | 19-03-2025 | 19-03-2025 | 22-03-2025 | [18 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-02-2025 | VESSEL DUE TO ARRIVE TODAY 10-02-2025 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTION FROM PORT TODAY | BV INSEPCTION TO BE DONE TODAY - LOADING WEDNESDAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR TOMORROW | LOADING PLANNED FOR FRIDAY | VEHICLE DELAYED NEW LOADING PLANNED - MONDAY 24-02-2025 | VEHICLE DELAYED NEW LOADING PLANNED - MONDAY 24-02-2025 | LOADING TODAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED LOADING THURSDAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED LOADING THURSDAY / FRIDAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED LOADING THURSDAY / FRIDAY | VEHICLE IN THE WORKSHOP BUSY WITH MAINTANCE - TO LOAD AND DISPATCH ONCE DONE - ESTIMATED TO LOAD NEXT WEEK | LOADING TODAY | LOADED TO DISPATCH DURBAN TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | DISPATCHED DURBAN ENROUTE JOHANNESBURG | ENROUTE SKILPADHEK BORDER | KAZUNGULA BOTSWANA SIDE CLEARING | KAZUNGULA BOTSWANA SIDE IN THE QUEUE TO CROSS TO ZAMBIAN SIDE | LIVINGSTONE ENROUTE SAKANIA BORDER | LUSAKA | DISPATCHING LUSAKA FOR SAKANIA BORDER | NDOLA - DISPATCHING FOR SAKANIA BORDER | SAKANIA DRC SIDE | KANYAKA AWAITING RELEASE | KAMOA BONDED TRUCK PARK | OFFLOADED 22-03-2025
BA2546 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | 3F606152 | CAT00745C3F606152 | TXW07705 | FML2312DSI2317 | COD 2025 171843 | CR84FXGP | WGR358GP / WGR365GP | ND60323 | VESSEL: GREY FOX Voy. 241201 - ETA DURBAN: 16-01-2024 | OFFLOADED 14-05-2025 | 15-04-2025 | 23-04-2025 |  | BV COMPLETED | 16-01-20245 | 23-04-2025 | 24-04-2025 | 24-04-2025 | 25-04-2025 | 25-04-2025 | 29-04-2025 | 29-04-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 07-05-2025 | 09-05-2025 | 09-05-2025 | 10-05-2025 | 10-05-2025 | 11-05-2025 | 11-05-2025 | 14-05-2025 | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV RSA CONFIRMED THE INSPECTION IS BOOKED FOR TOMORROW 23-04-2025 | BV INSPECTION TO BE DONE TODAY | VAN REENEN ENROUTE JOHANNESBURG | MOKOPANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | KAROI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | KABWE ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALSA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE | KASUMBALESA DRC SIDE AWAITING DUTIES TO BE PAID - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 14-05-2025
BA2553 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | 3F606177 | CAT00745L3F606177 | TXW07778 | FML2312DSI2339 | COD 2025 171843 | KB15KRGP | LL76KSGP | ND60325 | VESSEL: GREEN MOUNTAIN Voy. 241202 - ETA DURBAN: 31-01-2024 | OFFLOADED 14-05-2025 | 15-04-2025 | 23-04-2025 |  | BV COMPLETED | 31-03-2024 | 23-04-2025 | 24-04-2025 | 24-04-2025 | 25-04-2025 | 25-04-2025 | 29-04-2025 | 29-04-2025 | 02-05-2025 | 03-05-2025 | 04-05-2025 | 04-05-2025 | 05-05-2025 | 05-05-2025 | 07-05-2025 | 07-05-2025 | 10-05-2025 | 10-05-2025 | 11-05-2025 | 11-05-2025 | 14-05-2025 | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV RSA CONFIRMED THE INSPECTION IS BOOKED FOR TOMORROW 23-04-2025 | BV INSPECTION TO BE DONE TODAY | HOWICK ENROUTE JOHANNESBURG | PIENAARSRIVIER ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | KAROI ENROUTE CHIRUNDU BORDER | KAPIRI MPOSHE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE AWAITING SEAL PAYMNET | WHISKEY AWAITING DURIES PAYMENT AND RELEASE | WHISKEY AWAITING DURIES PAYMENT AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 14-05-2025
BA2560 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | 3F606132 | CAT00745L3F606132 | TXW07663 | FML2312DSI2318 | COD 2025 171843 | JP51CBGP | LC63BJGP / LL07VFGP | ND60324 | VESSEL: GREY FOX Voy. 241201 - ETA DURBAN: 16-01-2024 | OFFLOADED 15-05-2025 | 15-04-2025 | 23-04-2025 |  | BV COMPLETED | 16-01-2024 | 23-04-2025 | 24-04-2025 | 29-04-2025 | 30-04-2025 | 30-04-2025 | 01-05-2025 | 02-05-2025 | 03-05-2025 | 06-05-2025 | 07-05-2025 | 07-05-2025 | 08-05-2025 | 08-05-2025 | 10-05-2025 | 10-05-2025 | 13-05-2025 | 14-05-2025 | 14-05-2025 | 14-05-2025 | 15-05-2025 | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV RSA CONFIRMED THE INSPECTION IS BOOKED FOR TOMORROW 23-04-2025 | BV INSPECTION TO BE DONE TODAY | VAN REENEN ENROUTE JOHANNESBURG | PRETORIA AWAITING LIMPOPO PERMIT | PRETORIA AWAITING LIMPOPO PERMIT - TO DISPATCH PRETORIA TODAY | HAMMANSKRAAL ENROUTE BEIT BRIDGE BORDER | GWERU ENROUTE HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | DISPATCHING CHIRUNDU BORDER | LUSAKA ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE AWAITING DUTIES TO BE PAID - DAY 1 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD - DAY 1 | OFFLOADED 15-05-2025
BA2847 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | 3F606334 | CAT000745K3F606334 | TXW08126 | FML2501DSI2652 | COD 2025 171843 | CJ84RCZN | CD46KDZN | ND60326 | VESSEL: HOEGH BOREALIS Voy. 2 - ETA DURBAN: 26-01-2025 | OFFLOADED 15-05-2025 | 15-04-2025 | 23-04-2025 |  | BV COMPLETED | 26-01-2025 | 23-04-2025 | 24-04-2025 | 25-04-2025 | 25-04-2025 | 25-04-2025 | 29-04-2025 | 02-05-2025 | 03-05-2025 | 06-05-2025 | 07-05-2025 | 07-05-2025 | 08-05-2025 | 08-05-2025 | 10-05-2025 | 10-05-2025 | 13-05-2025 | 13-05-2025 | 13-05-2025 | 14-05-2025 | 15-05-2025 | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS, TAILGAIT & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | AT BONDED FACILITY - AWAITING FSS & BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV NUMBER RECEIVED - BV INSPECTION TO BE DONE TUESDAY 22-04-2025 | BV RSA CONFIRMED THE INSPECTION IS BOOKED FOR TOMORROW 23-04-2025 | BV INSPECTION TO BE DONE TODAY | HOWICK ENROUTE JOHANNESBURG | PUMULANI PLAZA PRETORIA ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | MVUMA ENROUTE HARARE | BANKET ENROUTE HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | DISPATCHING CHIRUNDU BORDER | SHIBALALA TOLL | KAPIRI MPOSHE ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | DISPATCHING WHISKEY | TENKE ENROUTE KOLWEZI | KAMOA BOND STORE - WAITING TO OFFLOAD - DAY 1 | OFFLOADED 15-05-2025
BA2939 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | 3F606329 | CAT00745T3F606329 | TXW08071 | FML2505DRE2692 | COD 2025 177082 | ND760431 | CM09LJZN / ND760428 | ND60415 |  | OFFLOADED 10-06-2025 - PLEASE ASSIST WITH PODs | 23-04-2025 | 15-05-2025 |  | BV COMPLETED |  |  |  | 21-05-2025 | 21-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | 26-05-2025 | 30-05-2025 | 30-05-2025 | 31-05-2025 | 01-06-2025 | 02-06-2025 | 02-06-2025 | 02-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 08-06-2025 | 10-06-2025 | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THURSDAY | BV NUMBER RECEIVED - INSPECTION BOOKING REQUEST SENT FOR THURSDAY - LOADING PLANNED FOR MONDAY | BV INSPECTION BOOKED FOR TODAY 15-05-2025 - LOADING PLANNED FOR MONDAY / TUESDAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR MONDAY / TUESDAY | LOADING TODAY | LOADED - AWAITING PERMIT - TO DISPATCH ONCE PERMIT IS RECEIVED | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | CHIRUNUD ZIM SIDE CLEARING | CHIRUNUD ZAM SIDE CLEARING | CHIRUNUD ZAM SIDE AWAITING CUSTOMS RELEASE | CHIRUNUD ZAM SIDE AWAITING CUSTOMS RELEASE | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY ALL DOCUMENTS READY - STARTING WITH FORMALITIES FOR RELEASE & EXIT - DAY 2 | WHISKEY IN THE QUEUE TO DISPATCH | KANYAKA WAITING RELEASE - PLEASE ASSIST | KANYAKA WAITING RELEASE - PLEASE ASSIST | KAMOA WAITING TO OFFLOAD | KAMOA BOND STORE WAITING TO OFFLOAD - DAY 2 PLEASE ASSIST | OFFLOADED 10-06-2025 - PLEASE ASSIST WITH PODs
BA2940 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | 3F606328 | CAT00745C3F606328 | TXW08061 | FML2505DRE2693 | COD 2025 177082 | ND754967 | ND654346 / ND526680 | ND60416 |  | OFFLOADED 10-06-2025 - PLEASE ASSIST WITH PODs | 23-04-2025 | 15-05-2025 |  | BV COMPLETED |  |  |  | 21-05-2025 | 21-05-2025 | 22-05-2025 | 25-05-2025 | 26-05-2025 | 26-05-2025 | 28-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 29-05-2025 | 31-05-2025 | 31-05-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 08-06-2025 | 10-06-2025 | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THURSDAY | BV NUMBER RECEIVED - INSPECTION BOOKING REQUEST SENT FOR THURSDAY - LOADING PLANNED FOR MONDAY | BV INSPECTION BOOKED FOR TODAY 15-05-2025 - LOADING PLANNED FOR MONDAY / TUESDAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR MONDAY / TUESDAY | LOADING TODAY | LOADED - AWAITING PERMIT - TO DISPATCH ONCE PERMIT IS RECEIVED | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | KWE KWE ENROUTE HARARE | CHIRUNUD ZIM SIDE CLEARING | CHIRUNUD ZAM SIDE CLEARING | KAPIRI MPOSHE ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 PLEASE ASSIST | WHISKEY ALL DOCUMENTS READY - STARTING WITH FORMALITIES FOR RELEASE & EXIT - DAY 3 | WHISKEY IN THE QUEUE TO DISPATCH | KANYAKA WAITING RELEASE - PLEASE ASSIST | KANYAKA WAITING RELEASE - PLEASE ASSIST | KAMOA WAITING TO OFFLOAD | KAMOA BOND STORE WAITING TO OFFLOAD - DAY 2 PLEASE ASSIST | OFFLOADED 10-06-2025 - PLEASE ASSIST WITH PODs
BA2851 | CAT336-08C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-56460 | MZR30096 | CAT00336CMZR30096 | D7E01661 | FML2412DSI2651 | COD 2025 194796 | CJ84RCZN | CD46KDZN | ND60437 | VESSEL: TARIFA Voy. 146 - ETA DURBAN: 04-02-2025 | OFFLOADED 20-06-2025 | 20-05-2025 | 26-05-2025 |  | BV COMPLETED | 04-02-2025 | 29-05-2025 | MIDDELBURG 29-05-2025 | MIDDELBURG 29-05-2025 | 30-05-2025 | 30-05-2025 | 02-06-2025 | 03-06-2025 | 05-06-2025 | 07-06-2025 | 08-06-2025 | 09-06-2025 | 09-06-2025 | 10-06-2025 | 12-06-2025 | 12-06-2025 | 17-06-2025 | 17-06-2025 | 17-06-2025 | 18-06-2025 | 20-06-2025 | [7 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY 26-05-2025 - LOADING PLANNED FOR WEDNESDAY 28-05-2025 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY 26-05-2025 - LOADING PLANNED FOR WEDNESDAY 28-05-2025 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 27-05-2025 - LOADING PLANNED FOR WEDNESDAY 28-05-2025 | BV INSPECTION COMPLETED - LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED, DISPATCHING DURBAN | MARBLE HALL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | MVUMA ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHINOYI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZIM SIDE CLEARING | KASUMBALESA BORDER ZIM SIDE CLEARING - DAY 2 | WHISKEY - DAY 1 | WHISKEY - DAY 5 | LIKASI ENROUTE KOLWEZI | KAMOA BOND STORE - WAITING TO OFFLOAD | KAMOA BOND STORE - WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST | OFFLOADED 20-06-2025
BA2546, BA2553, BA2560, BA2847 | 4 X CAT745 TAILGATES | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | N/A | N/A | N/A | FML2505DRE2694 | COD 2025 171843 | LG87RCGP | WJD486GP / WJD488GP | 2505DRE2694 |  | OFFLOADED 27-06-2025 | 15-04-2025 | 02-06-2025 | 12-06-2025 | BV COMPLETED |  | RCB 05-06-2025 | 05-06-2025 | 05-06-2025 | ZEERUTS 06-06-2025 | KOPFONTEIN BORDER 07-06-2025 | KOPFONTEIN BORDER 09-06-2025 | FRANCISTOWN 10-06-2025 | KAZUNGULA 10-06-2025 | KAZUNGULA 11-06-2025 | 13-06-2025 | 13-06-2025 | 13-06-2025 | 13-06-2025 | 15-06-2025 | 15-06-2025 | 20-06-2025 | 20-06-2025 | 20-06-2025 | 20-06-2025 | 27-06-2025 | [26 empty] | BV INSPECTION TO BE BOOKED NEXT WEEK - AWAITING CONFIRMATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR TOMORROW | BV INSPECTION DONE - VEHICLE DELAYED LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING FOR THE BORDER | ZEERUST ENROUTE KOPFONTEIN | ZEERUST ENROUTE KOPFONTEIN | KOPFONTEIN BORDER CLEARING | PALAPYE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | CHOMA ENROUTE NDOLA | KAPIRI ENROUTE KASUMBALESA BORDER | WHISKEY - DAY 2 | WHISKEY - DAY 3 | WHISKEY - DAY 4 | WHISKEY - IN THE QUEUE TO EXIT | KOLWEZI | KOLWEZI | KOLWEZI WAITING TO BE RELEASED FROM FIRST OFFLOADING POINT TO PROCEED TO SITE FOR OFFLOADING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASSIST | OFFLOADED 27-06-2025
BA2938, BA2939, BA2940 | 3 X CAT745 TAILGATES | BARTRAC EQUIPMNET - KAMOA COPPER SA | 01013-OX-55633 | N/A | N/A | N/A | FML2505DRE2694 | COD 2025 177082 | LG87RCGP | WJD486GP / WJD488GP | 2505DRE2694 |  | OFFLOADED 27-06-2025 | 23-04-2025 | 02-06-2025 | 07-06-2025 | BV COMPLETED |  | RCB 05-06-2025 | 05-06-2025 | 05-06-2025 | ZEERUTS 06-06-2025 | KOPFONTEIN BORDER 07-06-2025 | KOPFONTEIN BORDER 09-06-2025 | FRANCISTOWN 10-06-2025 | KAZUNGULA 10-06-2025 | KAZUNGULA 11-06-2025 | 13-06-2025 | 13-06-2025 | 13-06-2025 | 13-06-2025 | 15-06-2025 | 15-06-2025 | 20-06-2025 | 20-06-2025 | 20-06-2025 | 20-06-2025 | 27-06-2025 | [26 empty] | BV INSPECTION TO BE BOOKED NEXT WEEK - AWAITING CONFIRMATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR TOMORROW | BV INSPECTION DONE - VEHICLE DELAYED LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING FOR THE BORDER | ZEERUST ENROUTE KOPFONTEIN | ZEERUST ENROUTE KOPFONTEIN | KOPFONTEIN BORDER CLEARING | PALAPYE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | CHOMA ENROUTE NDOLA | KAPIRI ENROUTE KASUMBALESA BORDER | WHISKEY - DAY 2 | WHISKEY - DAY 3 | WHISKEY - DAY 4 | WHISKEY - IN THE QUEUE TO EXIT | KOLWEZI | KOLWEZI | KOLWEZI WAITING TO BE RELEASED FROM FIRST OFFLOADING POINT TO PROCEED TO SITE FOR OFFLOADING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASSIST | OFFLOADED 27-06-2025
BA2858 | EG20-T3 MINING GRADER | BARTRAC EQUIPMENT - KAMOA COPPER | 01013-OX-53578 | 21NK0103 | CAT00120CE9601121 | E7A65031 | FML2508DSI2711 | COD 2025 276166 | BCF1171ZM | BCF3312ZM | 2508DSI2711 | VESSEL: MSC AZOV Voy. MA532R Transhipment Vessel: MSC BEIJING Voy. ZF539A - ETA DURBAN: 09-11-2025 | OFFLOADED 10-12-2025 | 10-09-2025 | 12-11-2025 |  | BV INSPECTION DONE | 06-11-2025 | 14-11-2025 | 15-11-2025 | 16-11-2025 | MOKOPANE 16-11-2025 | GRB 16-11-2025 | GRB 19-11-2025 | FRANCISTOWN 20-11-2025 | KAZUNGULA BORDER 20-11-2025 | KAZUNGULA BORDER 25-11-2025 | 26-11-2025 | 27-11-2025 | 28-11-2025 | 28-11-2025 | 02-12-2025 | 03-12-2025 | 06-12-2025 | 06-12-2025 | 06-12-2025 | 07-12-2025 | 10-12-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 15-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 10-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 10-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 10-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 10-10-2025 | AWAIITNG VESSEL ARRIVAL - ETA DURBAN PORT - 10-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 23-10-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 04-11-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 04-11-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 04-11-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 04-11-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 04-11-2025 | AWAIITNG TRANSHIPMENT VESSEL DETAILS - ETA DURBAN PORT - 04-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 05-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 05-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 05-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 05-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 07-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 07-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 07-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 11-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 11-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 11-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 11-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 11-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 09-11-2025 | TRANSHIPMENT VESSEL DETAILS RECEIVED - ETA DURBAN PORT - 09-11-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2025 | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT - CURRENTLY AT BONDED FACILTY - TO UNPACK TODAY - BV INSPECTION TO BE ARRANGED FOR THIS WEEK | UNIT AT BONDED FACILITY - BV INSPECTION REQUESTED - AWAITING CONFIRMATION FROM BV | UNIT AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR TODAY | UNIT LOADED - TO DISPATCH FOR THE BORDER | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING AND WAITING RELEASE | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING AND WAITING RELEASE | KALOMO ENROUTE LUSAKA | KAPIRI ENROUTE NDOLA | NDOLA - BUSY WITH MAINTENANCE CHECK | KASUMBALESA ZAMBIAN SIDE CLEARING | KASUMBALESA ZAMBIAN SIDE CLEARING - DAY 3 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 10-12-2025

## OFFLOADED - 2024 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | KAMOA PO NUMBER | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY ARR | WHISKY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS
BA2016 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 45688 OX | 3F602150 | CAT00745E3F602150 | TXW06702 | FML2209DSI1742 | COD 2022 292164 | ND760431 | ND760424 / ND760428 | ND63615 | VESSEL: HOEGH ST. PETERSBURG Voy. 77 ETA: 05-10-2022 | OFFLOADED 22-11-2022 | 15-09-2022 | 19.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT ARRIVE IN DURBAN | 06.10.2022 | 31-10-2022 | 01.11.2022 | 01.11.2022 | 02.11.2022 | 03-11-2022 | 05-11-2022 | 06-11-2022 | 07-11-2022 | 08-11-2022 | 08-11-2022 | 09-11-2022 | 10-11-2022 | 13.11.2022 | 14.11.2022 | 15.11.2022 | 15.11.2022 | 16.11.2022 | 17.11.2022 | 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 04-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 04-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 04-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-09-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN PORT 05-10-2022 | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - PLANNING TO COLLECT TOMMROW THE 14/10/2022 | COLLECTING UNIT FROM P0ORT TODAY - BV INSPOECTION TO BE BOOKED FOR NEXT WEEK | UNIT TO BE COLLECTED FORM PORT - TRANSNET STILL STRIKING | UNIT TO BE COLLECTED FORM PORT - TRANSNET STILL STRIKING | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 19-10-2022 - LOADING DATE TO BE CONFIRMED | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING MONDAY 24-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING MONDAY 24-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING MONDAY 24-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING MONDAY 24-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 27-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 27-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 28-10-2022 | * UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH | DISPATCHING DURBAN TODAY | TRUCK AT DUNDEE EN-ROUTE TO BEIT BRIDGE | TRUCK AT MIDDELBURG EN-ROUTE TO BEIT BRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEIT BRIDGE | BEIT BRIDGE ZIM SIDE | CHINOYI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE IN THE QUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY - TO DISPATCH THIS MORNING FOR LUBUMBASHI | * VEHICLE CURRENTLY AT LIKASI ENROUTE KOLWEZI | * VEHICLE ON SITE WAITING TO OFLLOAD | * VEHICLE ON SITE WAITING TO OFLLOAD | * VEHICLE ON SITE WAITING TO OFLLOAD - DAY 5 | * VEHICLE ON SITE WAITING TO OFLLOAD - DAY 6 | OFFLOADED 22-11-2022 | OFFLOADED 22-11-2022
BA2086 | 1 X CAT930K WHEEL LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 45203 OX | P3K01288 | CAT0930KAP3K01288 | 45016442 | FML2209DSI1765 | COD 2022 302026 | NU112272 | ND629383 | ND63627 | VESSEL: SERENITY ACE Voy. 0108A ETA: 05-10-2022 | OFFLOADED 09-12-2022 | 29-09-2022 | 19.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT ARRIVE IN DURBAN | 06.10.2022 | 08-11-2022 | MIDDELBURG 08-11-2022 | MIDDELBURG 09-11-2022 | 09-11-2022 | 10-11-2022 | 13.11.2022 | 15.11.2022 | 17.11.2022 | 18.11.2022 | 18.11.2022 | 18.11.2022 | 18-11-2022 | 27-11-2022 | 28-11-2022 | 03.12.2022 | 04.12.2022 | 04.12.2022 | 07-12-2022 | 09-12-2022 | [6 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN PORT 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN PORT 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN PORT 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN PORT 05-10-2022 | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | COLLECTING UNIT FROM PORT TODAY | UNIT IS AT OUR FACILITY AWAITING BV AND LOADING DATE | UNIT IS AT OUR FACILITY - BV INSPECTION TOP BE BOOKED FOR MONDAY 17-10-2022 - LOADING DATE TO BE CONFIRMED | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TUESDAY 18-10-2022 - LOADING DATE TO BE CONFIRMED | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TUESDAY 18-10-2022 - LOADING DATE TO BE CONFIRMED | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 19-10-2022 - LOADING DATE TO BE CONFIRMED | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY 26-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY 26-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY 26-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY 26-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 27-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 28-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 31-10-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 02-11-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 02-11-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 04-11-2022 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 04-11-2022 | LOADING TODAY TO DISPATCH MONDAY | WAITING PERMIT, TO DISPATCH TODAY | CATO RIDGE ENROUTE JOHANNESBURG | MIDDELBURG | MUSINA TO PROCEED TO BEIT BRIDGE | BEIT BRIDGE RSA SIDE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MVUMA ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - DAY 3 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - DAY 4 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE FOR BA2286 IN ORDER TO DISPATCH | * VEHICLE CURRENTLY AT KISENDA ENROUTE KOLWEZI | * VEHICLE CURRENTLY AT KISENDA MINE WAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING ESCOURT | * VEHICLE CURRENTLY AT KOLWEZI PARKING | * VEHICLE CURRENTLY ON SITE AT BONDED WAREHOUSE | OFFLOADED 09-12-2022 | OFFLOADED 09-12-2022
BA2018 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 45688 OX | 3F602154 | CAT00745K3F602154 | TBA | FML2209DSI1773 | COD 2022 292164 PT02 | ND834401 | ND854241 | ND63688 | VESSEL: RED CEDAR VOY. 2271 ETA 14-12-2022 | OFFLOADED 18-01-2023 | 15-09-2022 | 20-12-2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT ARRIVE IN DURBAN | 18-12-2022 | 21-12-2022 | 21-12-2022 | 21-12-2022 | 22-12-2022 | 28-12-2022 | 30-12-2022 | 31-12-2022 | 01-01-2023 | 06-01-2023 | 06-01-2023 | 06-01-2023 | 07-01-2023 | 10-01-2023 | 10-01-2023 | 12-01-2023 | 12-01-2023 | 13-01-2023 | 14-01-2023 | 18-01-2023 | WAITING VESSEL DETAILS - ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2023 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 02/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 07/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 13/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 13/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 13/12/2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 14/12/2022 - BV INSPECTION PROVISIONALLY BOOKED FOR 15-12-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 14/12/2022 PM - BV INSPECTION MOVED TO MONDAY 19-12-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 11H00 TODAY 15/12/2022 PM - BV INSPECTION MOVED TO MONDAY 19-12-2022 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - DISPATCHING DURBAN TODAY | VEHICLE CURRENTLY AT MARBLE HALL EROUTE MUSINA BORDER | VEHICLE CURRENTLY AT NABOOMSPRUIT EROUTE MUSINA BORDER | VEHICLE CURRENTLY AT BEITBRIDGE AWAITING RELEASE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING PERMIT | VEHICLE CURRENTLY AT MASVINGO | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAM AWAITING PERMIT | VEHICLE CURRENTLY AT LUSAKA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE IN QUEUE TO CROSS | VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 3 | VEHICLE CURRENTLY AT LUBUMBASHI, WAITING ESCORT TO PROCEED TO KOLWEZI | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 2 | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 18-01-2023
BA2017 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 45688 OX | 3F602152 | CAT00745T3F602152 | TBA | FML2209DSI1772 | COD 2022 292164 | ND61605 | ND868372 | ND63774 | VESSEL: BRIGHT SKY VOY. 2269 ETA 17-01-2023 | OFFLOADED 16-02-2023 | 15-09-2022 | 25-01-2023 | BV INSPECTION COMPLETE | 17-01-2023 | 25-01-2023 | 26-01-2023 | 26-01-2023 | 27-01-2023 | 30-01-2023 | 31-01-2023 | 02-02-2023 | 03-02-2023 | 04-02-2023 | 04-02-2023 | 05-02-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | 13-02-2023 | 14-02-2023 | 14-02-2023 | 14-02-2023 | 16-02-2023 | WAITING VESSEL DETAILS - ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2023 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN 23-10-2022 | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | WAITING VESSEL DETAILS - ESTIMATED ETA DURBAN TBA | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 06/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 14/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 14/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 14/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 14/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 16/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 16/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 16/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 17/01/2023 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 17/01/2023 | VESSEL CURRENTLY IN AND WORKING | WAITING BOOKING CONFIRMATION FROM PORT TO COLLECT UNIT | VESSEL COMPLETED - UNIT TO BE COLLECTED FROM PORT - BV INSPECTION BOOKED FOR 25-01-2023 | UNIT COLLECTED FROM PORT, BV INSPECTION BOOKED FOR TOMORROW 25-01-2023 | BV INSPECTION BOOKED FOR TODAY 25-01-2023 - TO DISPATCH ONCE BV INSPECTION IS COMPLETED | BV INSPECTION COMPLETED - VEHICLE CURRENTLY AT WEENEN ENROUTE JOHANNESBURG | MARBLE HALL ENROUTE MUSINA | TRUCK IS AT BEITBRIDGE RSA SIDE AWAITING RELEASE | TRUCK IS AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | TRUCK IS AT MVUMA ENROUTE HARARE | TRUCK IS AT CHINOYI EN ROUTE CHIRUNDU | TRUCK IS AT CHIRUNDU ZAM SIDE | VEHICLE AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA ZAM CROSSING TO DRC SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE & SEAL REMOVAL | VEHICLE AT KANYAKA AWAITING RELEASE | VEHICLE AT KOLWEZI | VEHICLE AT ON SITE WAITING TO OFFLOAD | OFFLOADED 16-02-2023
BA2406 | CAT336-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49310 OX | GDY21752 | CAT00336JGDY21752 | NTB12060 | 2212DSI1869 | COD 2023 181769 | ND834401 | ND702944 | ND63862 | DALIAN HIGHWAY Voy 97 - ETA DURBAN 30-01-2023 | OFFLAODED 02-06-2023 | 24-04-2023 | 28-05-2023 | BV INSPECTION COMPLETE | 30-01-2023 | 09-05-2023 | MIDDELBURG 10-05-2023 | MIDDELBURG 10-05-2023 | 11-05-2023 | 11-05-2023 | 14-05-2023 | 15-05-2023 | 15-05-2023 | 17-05-2023 | 17-05-2023 | 19-05-2023 | 24-05-2023 | 25-05-2023 | 26-05-2023 | 31-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 02-06-2023 | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED | BV INSPECTION BOOKED FOR FRIDAY - LOADING NEXT WEEK | BV INSPECTION BOOKED FOR FRIDAY - LOADING NEXT WEEK | BV INSPECTION BOOKED FOR TODAY - LOADING NEXT WEEK | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE THURSDAY 04-05-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE THURSDAY 04-05-2023 | ESTIMATED LOADING DATE MONDAY 08-05-2023 - VEHICLE CURRENTLY UNDERGOING MAINTENANCE CHECKS | TRUCK IN WORKSHOP-PLANNING TO LOAD TOMORROW THE 09-05-2023 | TRUCK LOADED AND WILL DISPATCH DURBAN TODAY | NEW CASTLE ENROUTE JOHANNESBURG | MARBLE HALL ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | KWEKWE ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAPIRI MPOSHE ENROUTE KASUMBALESA | KAPIRI MPOSHE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN QUEUE TO PROCEED TO KASUMBLAESA | VEHICLE AT KASUMBLAESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBLAESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY UNDER CLEARANCE | VEHICLE AT WHISKEY UNDER CLEARANCE DAY 3 | VEHICLE AT WHISKEY UNDER CLEARANCE DAY 4 | VEHICLE AT LIKASI EN-ROUTE TO SITE | VEHICLE AT KAMOA AWAITING TO OFFLOAD | VEHICLE AT KAMOA AWAITING TO OFFLOAD DAY 2 | OFFLOADED 02-06-2023
BA2466 | 1 X CAT D8GC TRACTOR | BARTRAC / KAMOA COPPER SA | PO 49276OX | M8D00392 | CAT000D8CM800392 | TXJ02309 | 2305DSI2075 | COD 2023 218687 | ND674075 | ND308532 | 130286 | VESSEL: LIBERTY ACE Voy. 145 - ETA DURBAN 02-07-2023 | OFFLOADED 28-07-2023 | 12-06-2023 | 11-07-2023 | BV NUMBER RECEIVED | 03-07-2023 | 11-07-2023 | 13-07-2023 | 13-07-2023 | 14-07-2023 | 15-07-2023 | 18-07-2023 | 19-07-2023 | 20-07-2023 | 21-07-2023 | 22-07-2023 | 23-07-2023 | 25-07-2023(MOKAMBO) |  | 26-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 28-07-2023 | 28-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-07-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-07-2024 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-07-2024 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE BOOKED FOR TOMORROW 05-07-2023 | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW - PENDING AMENDED LICENSE | COLLECTED FROM PORT - AWAITING AMENDED LICENSE TO BOOK BV INSPECTION | COLLECTED FROM PORT - AWAITING AMENDED LICENSE TO BOOK BV INSPECTION | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION BOOKED FOR TODAY | VEHICLE CURRENTLY AT VOLKSRUST ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT VOLKSRUST COLLECTING PERMITS / ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT VOLKSRUST COLLECTING PERMITS / ENROUTE JOHANNESBURG | VEHICLE CURRENTLY PASSING POLOKWANE ENROUTE BEIT BRIDGE | VEHICLE CURRENTLY AT BEIT BRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | VEHICLE CURRENTLY AT PASSING CHIKOMBA ENROUTE HARARE | VEHICLE CURRENTLY CHIRUNDU CLEARING | VEHICLE CURRENTLY CHIRUNDU CLEARING | VEHICLE CURRENTLY AT NDOLA FILLING DIESEL BEFORE DISPATCHING | VEHICLE CURRENTLY AT MOKAMBO BORDER CLEARING | VEHICLE CURRENTLY AT MOKAMBO BORDER CLEARING | VEHICLE AT KOMBOVE EN-ROUTE TO KOLWEZI | VEHICLE AT MUTSHATASHA KOLWEZI | OFFLOADED 28-07-2023
BA2312 | 1 X CAT226B3 SKID STEER LOADER & FIRE SUPPRESSION SYSTEM | BARTRAC / KAMOA COPPER SA | PO 49763OX | DXZ03487 | CAT0226BCDXZ03487 | CZ209573 | 2211DSI1828 | COD 2023 230322 | B300BOZ | DS74ZFGP | ND63986 | VESSEL: NYK PAULA Voy. 2247W - ETA DURBAN 16-12-2022 | OFFLOADED 31-08-2023 | 27-06-2023 | 10-07-2023 | BV COMPLETED | 16-12-2023 | 11-07-2023 | 15-07-2023 | 20-07-2023 | 22-07-2023 | 28-07-2023 | 31-07-2023 | 03-08-2023 | 03-08-2023 | 08-08-2023 | 08-08-2023 | 09-08-2023 | 09-08-2023 | 10-08-2023 | 19-08-2023 | 19-08-2023 | 26-08-2023 | 26-08-2023 | 29-08-2023 | 29-08-2023 | 31-08-2023 | [13 empty] | AWAITING BV NUMBER AND FSS | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV INSPECTION BOOKED FOR 07-07-2023 | BV INSPECTION BOOKED FOR 07-07-2023 | BV INSPECTION BOOKED FOR MODAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - AWAITING PERMIT IN ORDER TO DISPATCH | VEHCILE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHCILE CURRENTLY AT PIETERMARITZBURG - AWAITING PERMIT TO DISPATCH | VEHCILE CURRENTLY AT PIETERMARITZBURG - AWAITING PERMIT TO DISPATCH | VEHCILE CURRENTLY AT COLENSO ENROUTE JOHANNESBURG | VEHCILE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHCILE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHCILE CURRENTLY AT JOHANNESBURG STILL WAITING PERMITS - DELAY IN PERMIT ISSUING | VEHCILE CURRENTLY AT JOHANNESBURG STILL WAITING PERMITS - DELAY IN PERMIT ISSUING - SHOULD RECEIVE IT TODAY | VEHCILE DISPATCHED JOHANNESBURG ENROUTE BORDER | VEHCILE AT GROBLERS BRIDGE BORDER CLEARING | HORSE OM BREAK DOWN AWAITING NEW HORSE TO LINK UP WITH THE TRAILER AND DISPATCH TO SITE.AMENDED PRE-ALERT TO FOLLOW | HORSE OM BREAK DOWN AWAITING NEW HORSE TO LINK UP WITH THE TRAILER TODAY AND PROCEED TO BEITBRIDGE BORDER FOR CLEARING | NEW HORSE ARRIVED TRUCK EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER WAITING RELEASE | TRUCK AT MASVINGO ENROUTE HARARE | TRUCK AT GWERU ENROUTE HARARE | TRUCK AT KWE KWE ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA ZAM SIDE AWAIITNG CLEARANCE | VEHICLE AT KASUMBALESA AWAITING VOC ON AMENDED TRUCK DETAILS DAY 5 | VEHICLE AT KASUMBALESA AWAITING VOC ON AMENDED TRUCK DETAILS DAY 6 | VEHICLE AT WHISKEY | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE AT WHISKEY WAITING RELEASE - DAY 4 | VEHICLE AT WHISKEY WAITING RELEASE - DAY 5 | VEHICLE AT WHISKEY WAITING RELEASE - DAY 6 | VEHICLE AT CONNEX LUBUMBASHI - WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 31-08-2023
BA2587 | 1 X CAT D8 TRACTOR | BARTRAC / KAMOA COPPER SA | TBA | M8D00425 | CAT00D8CMD00425 | TXJ02502 | 2307DSI2157 | COD 2023 254649 | NU112272 | ND868372 | ND60448 | VESSEL: ETERNAL ACE Voy. 0103A - ETA DURBAN 30-07-2023 | OFFLOADED 07-09-2023 | 27-07-2023 | 03-08-2023 | BV COMPLETED | 30-07-2023 | 14-08-2023 | 17-08-2023 | 17-08-2023 | 17-08-2023 | 18-08-2023 | 18-08-2023 | 21-08-2023 | 21-08-2023 | 23-08-2023 | 23-08-2023 | 24-08-2023 | 24-08-2023 | 26-08-2023 | 27-08-2023 | 27-08-2023 | 03-09-2023 | 03-09-2023 | 03-09-2023 | 05-09-2023 | 07-09-2023 | [13 empty] | AWAITING BV NUMBER AND FSS | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV RECEIVED AWAITING FSS IN ORDER TO ARRANGE FOR BV | BV INSPECTION BOOKED FOR 07-07-2023 | BV INSPECTION BOOKED FOR 07-07-2023 | BV INSPECTION BOOKED FOR MODAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - AWAITING PERMIT IN ORDER TO DISPATCH | VEHCILE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHCILE CURRENTLY AT PIETERMARITZBURG - AWAITING PERMIT TO DISPATCH | VEHCILE CURRENTLY AT PIETERMARITZBURG - AWAITING PERMIT TO DISPATCH | VEHCILE CURRENTLY AT COLENSO ENROUTE JOHANNESBURG | VEHCILE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHCILE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHCILE CURRENTLY AT JOHANNESBURG STILL WAITING PERMITS - DELAY IN PERMIT ISSUING | VEHCILE CURRENTLY AT JOHANNESBURG STILL WAITING PERMITS - DELAY IN PERMIT ISSUING - SHOULD RECEIVE IT TODAY | VEHCILE DISPATCHED JOHANNESBURG ENROUTE BORDER | VEHCILE AT GROBLERS BRIDGE BORDER CLEARING | HORSE OM BREAK DOWN AWAITING NEW HORSE TO LINK UP WITH THE TRAILER AND DISPATCH TO SITE.AMENDED PRE-ALERT TO FOLLOW | HORSE OM BREAK DOWN AWAITING NEW HORSE TO LINK UP WITH THE TRAILER TODAY AND PROCEED TO BEITBRIDGE BORDER FOR CLEARING | AWAIITNG VESSEL ARRIVAL AND BV NUMBER | AWAIITNG VESSEL ARRIVAL AND BV NUMBER | VESSEL ARRIVED AND WORKING - WAITING COMPLETION OF DISCHARGE | COLLECTING UNIT FROM PORT TODAY | COLLECTED FROM PORT - BV INSPECITON BOOKED FOR TOMORROW 03-08-2023 | BV INSPECITON BOOKED FOR TODAY | BV INSPECITON COMPLETED - LOADING PLANNED FOR NEXT WEEK | BV INSPECITON COMPLETED - LOADING PLANNED FOR NEXT WEEK | BV INSPECITON COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECITON COMPLETED - PLANNING TO LOAD 14-08-2023 | TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER UNDER CLEARANCE | TRUCK AT HARARE ENROUTE CHIRUNDU | TRUCK CHIRUNDU ZAM SIDE CLEARING | TRUCK DISPATCHED CHIRUNDU ZAM ENROUTE LUSAKA | VEHICLE AT KABWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT GOMES/WHISKEY WAITING RELEASE | VEHICLE AT GOMES/WHISKEY WAITING RELEASE - DAY 2 | VEHICLE AT GOMES/WHISKEY WAITING RELEASE - DAY 3 | VEHICLE AT WHISKEY WAITING RELEASE - DAY 4 | VEHICLE AT WHISKEY WAITING RELEASE - DAY 5 | VEHICLE AT LIKASI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFLLOAD | VEHICLE ON SITE WAITING TO OFLLOAD | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-09-2023
BA2446 | 1 X CATERPILLAR 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533OX | DXZ03582 | CAT0226BPDXZ03582 | CZ209881 | 2302DSI1964 | COD 2023 297095 | HL40KXGP | N/A | 2302DSI1964 | MSC HOUSTON V, IA310A - ETA 19-04-2023 | OFFLOADED | 20-09-2023 | 27-09-2023 | BV NUMBER RECEIVED | 19-04-2023 | 29-09-2023 | 29-09-2023 | 02-10-2023 | 03-10-2023 | GRB 03-10-2023 | M-DRIFT 04-10-2023 | FRANCISTOWN 04-10-2023 | KAZ 04-10-2023 | KAZ 05-10-2023 | 07-10-2023 | 11-10-2023 | 12-10-2023 | 16-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 20-10-2023 | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TUESDAY 26-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TUESDAY 26-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | LOADING TODAY | LOADED ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | MOKOPANE EN-ROUTE GROBLERS BRIDGE BORDER | DISPATCHING FROM MARTINS DRIFT BORDER ENROUTE KAZUNGULA | KAZUNGULA BOTSWANA SIDE CLEARING | LIVINGSTONE ENROUTE KASUMBALESA | LUSAKA ON BREAKDOWN - MECHANICS ARE BUSY WORKING ON IT | LUSAKA ON BREAKDOWN - MECHANICS ARE BUSY WORKING ON IT | CHISAMBA ENROUTE KASUMBALESA | KITWE ENROUTE MOKAMBO | MUFILIRA ENROUTE MOKAMBO | MOKAMBO DRC SIDE WAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED
BA2447 | 1 X CATERPILLAR 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533OX | DXZ03583 | CAT0226BKDXZ03583 | CZ209896 | 2302DSI1964 | COD 2023 297095 | HL40KXGP | N/A | 2302DSI1964 | MSC HOUSTON V, IA310A - ETA 19-04-2023 | OFFLOADED | 20-09-2023 | 27-09-2023 | BV NUMBER RECEIVED | 19-04-2023 | 29-09-2023 | 29-09-2023 | 02-10-2023 | 03-10-2023 | GRB 03-10-2023 | M-DRIFT 04-10-2023 | FRANCISTOWN 04-10-2023 | KAZ 04-10-2023 | KAZ 05-10-2023 | 07-10-2023 | 11-10-2023 | 12-10-2023 | 16-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 20-10-2023 | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TUESDAY 26-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TUESDAY 26-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | LOADING TODAY | LOADED ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | MOKOPANE EN-ROUTE GROBLERS BRIDGE BORDER | DISPATCHING FROM MARTINS DRIFT BORDER ENROUTE KAZUNGULA | KAZUNGULA BOTSWANA SIDE CLEARING | LIVINGSTONE ENROUTE KASUMBALESA | LUSAKA ON BREAKDOWN - MECHANICS ARE BUSY WORKING ON IT | LUSAKA ON BREAKDOWN - MECHANICS ARE BUSY WORKING ON IT | CHISAMBA ENROUTE KASUMBALESA | KITWE ENROUTE MOKAMBO | MUFILIRA ENROUTE MOKAMBO | MOKAMBO DRC SIDE WAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED
BA2322 | 1 X CATERPILLAR 980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533OX | MK900662 | CAT00980CMK900662 | P4E05567 | 2212DSI1879 | COD 2023 297095 | ND919947 | ND923085 | 132459 | MORNING CHANT V. 085 - ETA DURBAN 06-02-2023 | OFFLOADED 08-11-2023 | 20-09-2023 | 18-10-2023 | BV COMPLETED | 06-02-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 22-10-2023 | 23-10-2023 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 01-11-2023 | 01-11-2023 | 04-11-2023 | 04-11-2023 | 05-11-2023 | 05-11-2023 | 08-11-2023 | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | LOADING TODAY FROM WHSE - BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THURSDAY 28-09-2023 | LOADING FROM WHSE 02-10-2023 - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE NEXT WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE EARLY NEXT WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE EARLY NEXT WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING MONDAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | LOADING MONDAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | LOADING MONDAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | LOADING TODAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH DURBAN THIS AFTERNOON | BV INSPECTION BOOKED FOR TODAY - VEHICLE TO DISPATCH DURBAN THIS AFTERNOON | VEHCILE CURRENLTY AT NEWCASTLE ENROUTE JOHANNESBURG | VEHCILE CURRENLTY AT GROBLERSBRIDGE BORDER - AWAITING CLEARANCE | VEHCILE CURRENLTY AT CHIVU ZIM AWAITING CLEARANCE | VEHCILE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHCILE CURRENLTY AT CHIRUNDU EN-ROUTE TO MOKAMBO | VEHCILE CURRENLTY AT KABWE EN-ROUTE TO MOKAMBO | VEHCILE CURRENLTY AT MOKAMBO ZAM SIDE | VEHCILE CURRENLTY AT MOKAMBO ZAM SIDE | VEHCILE STILL AT MOKAMBO ZAM SIDE | VEHCILE STILL AT MOKAMBO ZAM SIDE | VEHCILE AT WHISKEY AWAITING RELEASE | VEHCILE AT WHISKEY AWAITING RELEASE | ON STIE WAITING TO OFFLOAD | ON STIE WAITING TO OFFLOAD | ON STIE WAITING TO OFFLOAD - DAY 2 | ON STIE WAITING TO OFFLOAD - UNIT WILL BE OFFLOADED TODAY | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2448 | 1 X CATERPILLAR 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | DXZ03584 | CAT0226BJDXZ03584 | CZ209867 | 2302DSI1964 | COD 2023 314178 | DT15SRGP | N/A | 2302DSI1964A | MSC HOUSTON V, IA310A - ETA 19-04-2023 | OFFLOADED | 13-10-2023 | 01-11-2023 | BV COMPLETED | 19-04-2023 | 03-11-2023 | 04-11-2023 | 04-11-2023 | 04-11-2023 | GRB 04-11-2023 | 04-11-2023 | FRANCISTOWN 04-11-2023 | KASUNGULA 05-11-2023 | KASUNGULA 05-11-2023 | 07-11-2023 | 07-11-2023 | 07-11-2023 | 07-11-2023 | 10-11-2023 | 10-11-2023 | 10-11-2023 | 10-11-2023 | 10-11-2023 | 11-11-2023 | 16-11-2023 | [19 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV INSPECTION BOOKED FOR TUESDAY 24-10-2023 - PLANNING TO DISPATCH DURBAN ON WEDNESDAY 25-10-2023 | BV INSPECTION BOOKED FOR TUESDAY 24-10-2023 - PLANNING TO DISPATCH DURBAN ON WEDNESDAY 25-10-2023 | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | BV INSPECTION TO BE DONE TODAY - LOADING TOMORROW | LOADING TODAY | LOADED - DISPATCHING DURBAN TODAY | LIVINSTONE ENROUTE SAKANIA BORDER | LIVINSTONE ENROUTE SAKANIA BORDER | VEHICLE CURRENLTY AT LUSAKA ENROUTE SAKANIA BORDER | VEHICLE AT SAKANIA WAITING T1 & TR8 IN ORDER TO PROCEED TO KASUMBALESA | VEHICLE AT SAKANIA WAITING T1 & TR8 IN ORDER TO PROCEED TO KASUMBALESA | VEHICLE TO DISPATCH FOR KASUMBALESA THIS MORNING | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD DAY 5 | OFFLOADED | OFFLOADED
BA2449 | 1 X CATERPILLAR 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | DXZ03585 | CAT0226BCDXZ03585 | CZ209901 | 2302DSI1964 | COD 2023 314178 | DT15SRGP | N/A | 2302DSI1964A | MSC HOUSTON V, IA310A - ETA 19-04-2023 | OFFLOADED | 13-10-2023 | 01-11-2023 | BV COMPLETED | 19-04-2023 | 03-11-2023 | 04-11-2023 | 04-11-2023 | 04-11-2023 | GRB 04-11-2023 | 04-11-2023 | FRANCISTOWN 04-11-2023 | KASUNGULA 05-11-2023 | KASUNGULA 05-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | 07-11-2023 | 10-11-2023 | 10-11-2023 | 10-11-2023 | 10-11-2023 | 10-11-2023 | 11-11-2023 | 16-11-2023 | [19 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED - AWAITING FSS IN ORDER TO BOOK BV INSPECTION | BV INSPECTION BOOKED FOR TUESDAY 24-10-2023 - PLANNING TO DISPATCH DURBAN ON WEDNESDAY 25-10-2023 | BV INSPECTION BOOKED FOR TUESDAY 24-10-2023 - PLANNING TO DISPATCH DURBAN ON WEDNESDAY 25-10-2023 | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | AWAITING AMENDED BV LICENCE IN ORDER TO DO BV AND LOAD THE TRUCK | BV INSPECTION TO BE DONE TODAY - LOADING TOMORROW | LOADING TODAY | LOADED - DISPATCHING DURBAN TODAY | LIVINSTONE ENROUTE SAKANIA BORDER | LIVINSTONE ENROUTE SAKANIA BORDER | VEHICLE CURRENLTY AT LUSAKA ENROUTE SAKANIA BORDER | VEHICLE AT SAKANIA WAITING T1 & TR8 IN ORDER TO PROCEED TO KASUMBALESA | VEHICLE AT SAKANIA WAITING T1 & TR8 IN ORDER TO PROCEED TO KASUMBALESA | VEHICLE TO DISPATCH FOR KASUMBALESA THIS MORNING | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD DAY 5 | OFFLOADED | OFFLOADED
BA2322 | 1 X CATERPILLAR 980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533OX | MK900662 | CAT00980CMK900662 | P4E05567 | 2212DSI1879 | COD 2023 297095 | ND919947 | ND923085 | 132459 | MORNING CHANT V. 085 - ETA DURBAN 06-02-2023 | OFFLOADED 08-11-2023 | 20-09-2023 | 18-10-2023 | BV COMPLETED | 06-02-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 22-10-2023 | 23-10-2023 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 01-11-2023 | 01-11-2023 | 04-11-2023 | 04-11-2023 | 05-11-2023 | 05-11-2023 | 08-11-2023 | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | AWAITING BV NUBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR WEDNESDAY 27-09-2023 | LOADING TODAY FROM WHSE - BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THURSDAY 28-09-2023 | LOADING FROM WHSE 02-10-2023 - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE NEXT WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE EARLY NEXT WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE EARLY NEXT WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING FROM WHSE THIS WEEK - BV INSPECTIO TO BE DONE ONCE LOADED | LOADING MONDAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | LOADING MONDAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | LOADING MONDAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | LOADING TODAY 16-10-2023 - BV INSPECTION TO BE DONE TUESDAY 17-10-2023 | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH DURBAN THIS AFTERNOON | BV INSPECTION BOOKED FOR TODAY - VEHICLE TO DISPATCH DURBAN THIS AFTERNOON | VEHCILE CURRENLTY AT NEWCASTLE ENROUTE JOHANNESBURG | VEHCILE CURRENLTY AT GROBLERSBRIDGE BORDER - AWAITING CLEARANCE | VEHCILE CURRENLTY AT CHIVU ZIM AWAITING CLEARANCE | VEHCILE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHCILE CURRENLTY AT CHIRUNDU EN-ROUTE TO MOKAMBO | VEHCILE CURRENLTY AT KABWE EN-ROUTE TO MOKAMBO | VEHCILE CURRENLTY AT MOKAMBO ZAM SIDE | VEHCILE CURRENLTY AT MOKAMBO ZAM SIDE | VEHCILE STILL AT MOKAMBO ZAM SIDE | VEHCILE STILL AT MOKAMBO ZAM SIDE | VEHCILE AT WHISKEY AWAITING RELEASE | VEHCILE AT WHISKEY AWAITING RELEASE | ON STIE WAITING TO OFFLOAD | ON STIE WAITING TO OFFLOAD | ON STIE WAITING TO OFFLOAD - DAY 2 | ON STIE WAITING TO OFFLOAD - UNIT WILL BE OFFLOADED TODAY | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2593 | 1 X CATERPILLAR 428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49455 OX | L7D01657 | CAT00428LL7D01657 | C4Z14529 | 2310DSI2232 | COD 2023 297095 | AKB 2617 | AID 4480 ZM | 2310DSI2232 | BLUE MASTER II Voy. 231219 - ETA 17-11-2023 | OFFLOADED 19-12-2023 | 24-10-2023 | 23-11-2023 | BV NUMBER RECEIVED | 17-11-2023 | 24-11-2023 | 25-11-2023 | 25-11-2023 | 25-11-2023 | GRB 25-11-2023 | GRB 28-11-2023 | FRANCISTOWN 28-11-2023 | KAZUNGULA 28-11-2023 | KAZUNGULA 29-11-2023 | 29-11-2023 | 02-12-2023 | 03-12-2023 | 04-12-2032 | 08-12-2023 | 08-12-2023 | 10-12-2023 | 10-12-2023 | 11-12-2023 | 11-12-2023 | 19-12-2023 | [15 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-11-2023 | VESSEL ARRIVED AND BUSY WORKING | UNIT TO BE COLLECTED FROM PORT TODAY/TOMORROW MORNING - BV INSPECTION BOOKED FOR THURSDAY 23-11-2023 | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR THURSDAY 23-11-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - LAODING TODAY | GROBLERS BRIDGE BORDER CLEARING | NATA ENROUTE KAZUNGULA BORDER | DISPATCHED KAZUNGULA ENROUTE KASUMBALESA | VEHICLE IN LUSAKA - DOING TRIP CHECK BEFORE DISPATCHING FOR KASUMBALESA | VEHICLE IN LUSAKA - DOING TRIP CHECK BEFORE DISPATCHING FOR KASUMBALESA | DISPATCHING LUSAKA TODAY FOR KASUMBALESA | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER CLEARING | KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC | KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASSIST | ON SITE WAITING TO OFFLOAD - DAY 3 PLEASE ASSIST | ON SITE WAITING TO OFFLOAD - DAY 8 PLEASE ASSIST | OFFLOADED 19-12-2023 | OFFLOADED 19-12-2023
BA2611 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533 OX | KGX00492 | CAT000D8EKGX00492 | TXJ02632 | 2311DSI2276 | COD 2023 297095 | BCC2927ZM | BCE473ZM | ND61160 | VESSEL: LORD VISHNU 057- Transhipment Vessel: CSAV RIO NEVADO Voy. 14A ETA 28/11/2023 | OFFLOADED | 24-10-2023 | 01-12-2023 | BV NUMBER RECEIVED | 28-11-2023 | 05-12-2023 | 06-12-2023 | 07-12-2023 | 07-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 13-11-2023 | 13-11-2023 | 14-12-2023 | 14-12-2023 | 15-12-2023 | 15-12-2023 | 22-12-2023 | 23-12-2023 | 26-12-2023 | 26-12-2023 | 28-12-2023 | [18 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-11-2023 | VESSEL ARRIVED AND CURRENTLY WORKING | VESSEL ARRIVED AND CURRENTLY WORKING - TO LOAD UNIT FROM PORT | COLLECTED FORM PORT YESTERDAY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PERMIT BEFORE DISPATCHING DURBAN | CAMPERDOWN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | BELA BELA ENROUTE MUSINA | MUSINA CLEARING | CHIRUNDU ZAM SIDE | CHIRUNDU ZAM SIDE | KATUBA ENROUTE KASUMBALESA | KITWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - ELECTION DAY | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2610 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533 OX | M8D00450 | CAT000D8EM8D00450 | TXJ02547 | 2311DSI2302 | COD 2023 297095 | ND570587 | ND702944 | ND61185 | VESSEL: AQUAMARINE ACE Voy. 0133A - ETA DURBAN: 14-12-2023 | OFFLOADED 23-01-2024 | 24-10-2023 | 18-12-2023 | BV NUMBER RECEIVED | 14-12-2023 | 19-12-2023 | MIDDELBURG 19-12-2023 | MIDDELBURG 20-12-2023 | 20-12-2023 | 21-12-2023 | 23-12-2023 | 23-12-2023 | 27-12-2023 | 04-01-2024 | 05-01-2024 | 05-01-2024 | 05-01-2024 | 06-01-2024 | 10-01-2024 | 10-01-2024 | 15-01-2024 | 15-01-2024 | 16-01-2024 | 18-01-2024 | [50 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-12-2023 | VEHICLE CURRENTLY AT LADYSMITH ENROUTE JOHANNESBURG | MIDDELBURG AWAITING LIMPOPO PERMITS | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | CHIRUNDU ZIM SIDE | CHIRUNDU BORDER | CHIRUNDU BORDER UNDEGOING CLEARANCE | CHIRUNDU BORDER UNDEGOING CLEARANCE TO DISPATCH TOMMROW THE 03/01/2024 | CHIRUNDU BORDER UNDEGOING CLEARANCE TO DISPATCH THE 04/01/2024 | CHIRUNDU BORDER DISPATCHED EN-ROUTE TO KASUMBALESA | TRUCK AT KAPIRI EN-ROUTE TO KASUMBALESA | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 4 | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE - DAY 2 | WHISKEY WAITING INSURANCE & RELEASE - DAY 5 | WHISKEY WAITING INSURANCE & RELEASE - DAY 6 | VEHICLE CURRENLTY AT TENKE ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD-3 DAYS STANDING TIME APPLICABLE | VEHICLE ON SITE WAITING TO OFFLOAD-4 DAYS STANDING TIME APPLICABLE | OFFLOADED 23-01-2024
BA2639 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | KGX00494 | CAT000D8TKGX00494 | TBA | 2311DSI2308 | COD 2023 314178 | ADC4410 | ADE9253ZM | ND61198 | VESSEL: PROCYON LEADER V. 076 - ETA DURBAN 03-01-2024 | OFFLOADED 31-01-2024 | 06-12-2023 | 05-01-2024 | BV COMPLETED | 04/01/2024 | 08-01-2024 | 10-01-2024 | 11-01-2024 | 12-01-2024 | 12-01-2024 | 13-01-2024 | 13-01-2024 | 14-01-2024 | 16-01-2024 | 17-01-2024 | 18-01-2024 | 19-01-2024 | 22-01-2024 | 24-01-2024 | 24-01-2024 | 25-01-2024 | 25-01-2024 | 26-01-2024 | 28-01-2024 | 31-01-2024 | [41 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-01-2024 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | COLLECTING FROM PORT TODAY AND BV BOOKED FOR FRIDAY THE 05/01/2024 | BV BOOKED FOR FRIDAY THE 05/01/2024 | BV INSPECTION COMPLETED - TO DISPATCH FROM DURBAN TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR THE BORDER | MUSINA ENROUTE BEIT BRIDGE BORDER | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE TO DISPATCH TODAY | CHIRUNDU ZAM SIDE - WAITING TO DISPATCH | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILILBOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY DISPATCHING TODAY | VEHICLE CURRENTLY AT LUAMBO EN ROUTE TO KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 31-01-2024
BA2640 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | KGX00495 | CAT000D9PKGX00495 | TBA | 2311DSI2309 | COD 2023 314178 | FZC404MP | HKL784MP | ND61199 | VESSEL: PROCYON LEADER V. 076 - ETA DURBAN 03-01-2024 | OFFLOADED 08-02-2024 | 06-12-2023 | 05-01-2024 | BV COMPLETED | 04/01/2024 | 08-01-2024 | MIDDELBURG 10-01-2024 | MIDDELBURG 11-01-2024 | 12-01-2024 | 16-01-2024 | 19-01-2024 | 21-01-2024 | 24-01-2024 | 24-01-2024 | 25-01-2024 | 26-01-2024 | 26-01-2024 | 27-01-2024 | 31-01-2024 | 31-01-2024 | 01-02-2024 | 01-02-2024 | 04.02.2024 | 05.02.2024 | 08-02-2024 | [41 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-12-2023 | OFFLOADED | OFFLOADED | VESSEL IS IN AND WORKING | COLLECTING FROM PORT TODAY AND BV BOOKED FOR FRIDAY THE 05/01/2024 | BV BOOKED FOR FRIDAY THE 05/01/2024 | BV INSPECTION COMPLETED - TO DISPATCH FROM DURBAN TODAY | MOOI REVIER ENROUTE JOHANNESBURG | ERMELO ENROUTE MUSINA | DISPATCHING MIDDELBURG FOR BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE - AWAITING ZIM PERMIT | BEIT BRIDGE - AWAITING ZIM PERMIT | BEIT BRIDGE - AWAITING ZIM PERMIT | BEITBRIDGE - AWAITING ZIM PERMIT | TRUCK IS AT MVUMA EN-ROUTE TO CHIRUNDU | TRUCK IS AT VUTI EN-ROUTE TO CHIRUNDU | TRUCK IS AT CHIRUNDU AWAITING RELEASE | TRUCK IS AT CHIRUNDU AWAITING RELEASE | TRUCK IS AT KAFUE EN-ROUTE TO KASUMBALESA | KASUMBALESA ZAM SIDE | KASUMBALESA DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING EXCORTS | LUBUMBASHI AWAITING EXCORTS | VEHICLE AT KAMOA BOND STORE | VEHICLE AT KAMOA BOND STORE - PLEASE ASSIST WITH OFFLOADING | VEHICLE AT KAMOA BOND STORE - PLEASE ASSIST WITH OFFLOADING | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08-02-2024
BA2621 | CAT UG20 WHEEL LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49533 OX | SZN20397 | CAT0120KPSZN20397 | TX711534 | 2310DSI2240 | COD 2023 297095 | BCF1091ZM | BCF6142ZM | 2310DSI2240 | VESSEL: MEARSK SEBAROK - Transhipment Vessel: SAN FERNADO Voy. 346S - ETA Durban: 02-01-2024 | OFFLOADED 14-02-2024 | 24-10-2023 | 10-01-2024 | BV NUMBER RECEIVED | 15-01-2023 | 17-01-2023 | 17-01-2024 | 17-01-2024 | 18-01-2024 | 19-01-2024 | 20-01-2024 | 21-01-2024 | 22-01-2024 | 23-01-2024 | 24-01-2024 | 26-01-2024 | 30-01-2024 | 31-01-2024 | 06-02-2024 | 07-02-2024 | 09-02-2024 | 09-02-2024 | 12-02-2024 | 13-02-2024 | 14-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-12-2023 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - BV INSPECTION TO BE BOOKED FOR WEDNESDAY 10-01-2024 | BV INSPECTION BOOKED FOR 10-01-2024 - AWAITING COMPLETION | BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR 15-01-2024 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 15-01-2024 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 15-01-2024 | LOADING TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT HILTON ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENLTY AT MOOKGOPONG ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENLTY AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO CHIRUNDU | VEHICLE CURRENLTY AT CHISAMBA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT NDOLA UNDER GOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA UNDER GOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING CLEARANCE AND IN THE QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING CLEARANCE AND IN THE QUEUE TO KASUMBALESA | VEHICLE BEFORE KASUMBALESA AND SHOULD CROSS TO DRC SIDE PM TODAY | VEHICLE KASUMBALESA BORDER | VEHICLE KASUMBALESA ZAM SIDE CLEARING | VEHICLE KASUMBALESA DRC SIDE AWAITNG CLEARANCE | VEHICLE KASUMBALESA DRC SIDE AWAITNG RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITNG CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITNG CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITNG RELEASE | VEHICLE CURRENTLY AT KOLWEZI EN-ROUTE TO KAMOA | VEHICLE CURRENTLY AT KAMOA AWAITING TO OFFLOAD | VEHICLE CURRENTLY AT KAMOA AWAITING TO OFFLOAD | VEHICLE CURRENTLY AT KAMOA AWAITING TO OFFLOAD | VEHICLE CURRENTLY AT KAMOA AWAITING TO OFFLOAD | OFFLOADED 14-02-2024
BA2588 | CAT CS74B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 49615 OX | B7M00449 | CATCS74BPB7M00449 | E7A59615 | FML2307DSI2158 | COD 2024 130953 | ND570587 | ND627367 | ND64684 | VESSEL: BANGKOK HIGHWAY V. 148 ETA DURBAN 05-09-2023 | OFFLOADED 27-03-2024 | 19-02-2024 | 07-03-2024 | BV NUMBER RECEIVED | 05-09-2023 | 07-03-2024 | MIDDELBURG 08-03-2024 | MIDDELBURG 08-03-2024 | 09-03-2024 | 09-03-2024 | 11-03-2024 | 12-03-2024 | 13-03-2024 | 15-03-2024 | 15-03-2024 | 16-03-2024 | 16-03-2024 | 16-03-2024 | 20-03-2024 | 20-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 27-03-2024 | [89 empty] | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THURSDAY | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | AWAITING CO-LOAD BA2632 TO ARRIVE IN DURBAN | BV INSPECTION IS BOOKED FOR TODAY AWAITING LOADING DATE ONCE BV IS DONE | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MIDDELBURG ENROUTE MUSINA | VEHICLE DISPATCHING FROM BEIT BRIDGE ZIM SIDE | VEHICLE GWERU ENROUTE HARARE | VEHICLE MAKUTI ENROUTE CHIRUNDU | VEHICLE CHIRUNDU ZAM SIDE | VEHICLE CHIRUNDU ZAM SIDE | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2599 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01724 | CAT00428LL7D01724 | TBA | FML2401DSI2361 | COD 2024 128543 | NU112272 | ND629383 | ND64681 | VESSEL: RED CEDAR Voy,241210 - ETA: 24-02-2024 | OFFLOADED 27-03-2024 | 16-02-2024 | 29-02-2024 | BV COMPLETED | 24-02-2024 | 03-03-2024 | MIDDELBURG 04-03-2024 | 05-03-2024 | 05-03-2024 | 07-03-2024 | 08-03-2024 | 10-03-2024 | 11-03-2024 | 14-03-2024 | 14-03-2024 | 15-03-2024 | 15-03-2024 | 15-03-2024 | 18-03-2024 | 19-03-2024 | 21-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 27-03-2024 | [83 empty] | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | VESSEL ARRIVED CURRENTLY DISCHARGING CARGO | BV INSPECTION BOOKED FOR 29-02-2024 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 04-03-2024 | MIDDELBURG ENROUTE MUSINA | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE RSA SIDE | TRUCK AT RUTENGA ENROUTE HARARE | TRUCK AT HARARE ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT KABWE ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA DRC SIDE | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI | TRUCK AT KOLWEZI PARKING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2600 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | 7D01725 | CAT00428HL7D01725 | TBA | FML2401DSI2362 | COD 2023 297095 | NU112272 | ND629383 | ND64681 | VESSEL: RED CEDAR Voy,241210 - ETA: 24-02-2024 | OFFLOADED 27-03-2024 | 13-02-2024 | 29-02-2024 | BV COMPLETED | 24-02-2024 | 03-03-2024 | MIDDELBURG 04-03-2024 | 05-03-2024 | 05-03-2024 | 07-03-2024 | 08-03-2024 | 10-03-2024 | 11-03-2024 | 14-03-2024 | 14-03-2024 | 15-03-2024 | 15-03-2024 | 15-03-2024 | 18-03-2024 | 19-03-2024 | 21-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 27-03-2024 | [83 empty] | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | VESSEL ARRIVED CURRENTLY DISCHARGING CARGO | BV INSPECTION BOOKED FOR 29-02-2024 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 04-03-2024 | MIDDELBURG ENROUTE MUSINA | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE RSA SIDE | TRUCK AT RUTENGA ENROUTE HARARE | TRUCK AT HARARE ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT KABWE ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA DRC SIDE | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI | TRUCK AT KOLWEZI PARKING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2619 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01745 | CAT00428TL7D01745 | C4Z14581 | FML2402DSI2390 | COD 2023 297095 | ND61605 | ND868372 | ND64686 | VESSEL: HOEGH TOKYO V. 111 ETA DURBAN: 04-03-2024 | OFFLOADED 27-03-2024 | 16-02-2024 | 07-03-2024 | BV NUMBER RECEIVED | 03-03-2024 | 09-03-2024 | MIDDELBURG 09-03-2024 | MIDDELBURG 10-03-2024 | 11-03-2024 | 11-03-2024 | 12-03-2024 | 14-03-2024 | 15-03-2024 | 15-03-2024 | 16-03-2024 | 18-03-2024 | 18-03-2024 | 19-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 27-03-2024 | [89 empty] | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 04-03-2024 | VESSEL IS IN AND WORKING | BV INSPECTION IS BOOKED FOR TODAY PLANNED TO LOAD TOMMROW THE 07/03/2024 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT CATO RIDGE ENROUTE MUSAINA | TRUCK AT MARBLE HALL ENROUTE MUSAINA | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT MVUMA ENROUTE HARARE | TRUCK ENROUTE HARARE | TRUCK AT KAROI ENROUTE CHIRUNDU | TRUCK AT KABWE ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA ZAM SIDE AWAITING CLEARING DOCS | TRUCK AT KASUMBALESADRC SIDE AWAITING CLEARING DOCS | TRUCK AT WHISKEY AWAITING CLEARANCE AND RELEASE | TRUCK AT WHISKEY AWAITING CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2622 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01747 | CAT00428KL7D01747 | C4Z14580 | FML2402DSI2391 | COD 2023 297095 | ND61605 | ND868372 | ND64686 | VESSEL: HOEGH TOKYO V. 111 ETA DURBAN: 04-03-2024 | OFFLOADED 27-03-2024 | 16-02-2024 | 07-03-2024 | BV NUMBER RECEIVED | 03-03-2024 | 09-03-2024 | MIDDELBURG 09-03-2024 | MIDDELBURG 10-03-2024 | 11-03-2024 | 11-03-2024 | 12-03-2024 | 14-03-2024 | 15-03-2024 | 15-03-2024 | 16-03-2024 | 18-03-2024 | 18-03-2024 | 19-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 27-03-2024 | [89 empty] | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 04-03-2024 | VESSEL IS IN AND WORKING | BV INSPECTION IS BOOKED FOR TODAY PLANNED TO LOAD TOMMROW THE 07/03/2024 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT CATO RIDGE ENROUTE MUSAINA | TRUCK AT MARBLE HALL ENROUTE MUSAINA | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT MVUMA ENROUTE HARARE | TRUCK ENROUTE HARARE | TRUCK AT KAROI ENROUTE CHIRUNDU | TRUCK AT KABWE ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA ZAM SIDE AWAITING CLEARING DOCS | TRUCK AT KASUMBALESADRC SIDE AWAITING CLEARING DOCS | TRUCK AT WHISKEY AWAITING CLEARANCE AND RELEASE | TRUCK AT WHISKEY AWAITING CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2629 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01746 | CAT00428PL7D01746 | C4Z14582 | FML2402DSI2392 | COD 2023 297095 | ND4912424 | ND702944 | ND64685 | VESSEL: HOEGH TOKYO V. 111 ETA DURBAN: 04-03-2024 | OFFLOADED 27-03-2024 | 16-02-2024 | 07-03-2024 | BV NUMBER RECEIVED | 03-03-2024 | 07-03-2024 | MIDDELBURG 08-03-2024 | MIDDELBURG 08-03-2024 | 09-03-2024 | 09-03-2024 | 10-03-2024 | 11-03-2024 | 12-03-2024 | 15-03-2024 | 16-03-2024 | 17-03-2024 | 17-03-2024 | 18-03-2024 | 20-03-2024 | 20-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 27-03-2024 | [89 empty] | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 04-03-2024 | VESSEL IS IN AND WORKING | BV INSPECTION IS BOOKED FOR TODAY PLANNED TO LOAD TOMMROW THE 07/03/2024 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MIDDELBURG ENROUTE MUSINA | TRUCK AT RUTENGA ENROUTE HARARE | TRUCK AT HARARE ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT KASUMBALESA ZAM SIDE | TRUCK AT KASUMBALESA DRC SIDE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2631 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01750 | CAT00428KL01750 | C4Z14583 | FML2402DSI2393 | COD 2023 297095 | ND4912424 | ND702944 | ND64685 | VESSEL: HOEGH TOKYO V. 111 ETA DURBAN: 04-03-2024 | OFFLOADED 27-03-2024 | 16-02-2024 | 07-03-2024 | BV NUMBER RECEIVED | 03-03-2024 | 07-03-2024 | MIDDELBURG 08-03-2024 | MIDDELBURG 08-03-2024 | 09-03-2024 | 09-03-2024 | 10-03-2024 | 11-03-2024 | 12-03-2024 | 15-03-2024 | 16-03-2024 | 17-03-2024 | 17-03-2024 | 18-03-2024 | 20-03-2024 | 20-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 27-03-2024 | [89 empty] | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 04-03-2024 | VESSEL IS IN AND WORKING | BV INSPECTION IS BOOKED FOR TODAY PLANNED TO LOAD TOMMROW THE 07/03/2024 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MIDDELBURG ENROUTE MUSINA | TRUCK AT RUTENGA ENROUTE HARARE | TRUCK AT HARARE ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT KASUMBALESA ZAM SIDE | TRUCK AT KASUMBALESA DRC SIDE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2632 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01751 | CAT00428JL7D01751 | C4Z14588 | FML2402DSI2394 | COD 2023 297095 | ND570587 | ND627367 | ND64684 | VESSEL: HOEGH TOKYO V. 111 ETA DURBAN: 04-03-2024 | OFFLOADED 27-03-2024 | 19-02-2024 | 07-03-2024 | BV NUMBER RECEIVED | 05-09-2023 | 07-03-2024 | MIDDELBURG 08-03-2024 | MIDDELBURG 08-03-2024 | 09-03-2024 | 09-03-2024 | 11-03-2024 | 12-03-2024 | 13-03-2024 | 15-03-2024 | 15-03-2024 | 16-03-2024 | 16-03-2024 | 16-03-2024 | 20-03-2024 | 20-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | 27-03-2024 | [89 empty] | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 03-03-2024 | AWAITING VESSEL ARRIVAL - ETA 04-03-2024 | VESSEL IS IN AND WORKING | BV INSPECTION IS BOOKED FOR TODAY AWAITING LOADING DATE ONCE BV IS DONE | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MIDDELBURG ENROUTE MUSINA | VEHICLE DISPATCHING FROM BEIT BRIDGE ZIM SIDE | VEHICLE GWERU ENROUTE HARARE | VEHICLE MAKUTI ENROUTE CHIRUNDU | VEHICLE CHIRUNDU ZAM SIDE | VEHICLE CHIRUNDU ZAM SIDE | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | VEHICLE AT WHISKEY AWAITING FINAL RELEASE AND CLEARANCE | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | ON SITE WAITING TO OFFLOAD - ARRIVED 22-03-2024 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-03-2024 | OFFLOADED 27-03-2024
BA2556 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | 3F606206 | CAT00745J3F606206 | TBA | FML2401DSI2360 | COD 2023 314178 | ND431926 | ND926165 | 2401DSI2360 | VESSEL: RED CEDAR Voy,241210 - ETA: 24-02-2024 | OFFLOADED | 13-02-2024 | 29-02-2024 | BV COMPLETED | 24-02-2024 | 04-03-2024 | 08-03-2024 | 10-03-2024 | 11-03-2024 | 11-03-2024 | 14-03-2024 | 15-03-2024 | 16-03-2024 | 20-03-2024 | 20-03-2024 | 20-03-2024 | 20-03-2024 | MOKAMBO 20-03-2024 | MOKAMBO 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 04-04-2024 | 06-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 26-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | AWAITING VESSEL ARRIVAL - ETA 24-02-2024 | VESSEL ARRIVED CURRENTLY DISCHARGING CARGO | BV INSPECTION BOOKED FOR 29-02-2024 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 04-03-2024 | DISPATCHING DURBAN TODAY | TRUCK DISPATCHED DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT UMLAAS EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT NEW CASTLE ENROUTE MUSINA | TRUCK AT NEW POLOKWANE ENROUTE MUSINA | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | TRUCK AT CHIVI ENROUTE HARARE | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT KAPIRI EN-ROUTE TO MOKAMBO BORDER | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE - DAY 5 - PLEASE URGNETLY ASSIT WITH RELEASE | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE - DAY 6 - PLEASE URGNETLY ASSIT WITH RELEASE | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE - DAY 7 - PLEASE URGNETLY ASSIT WITH RELEASE | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE - DAY 8 - PLEASE URGNETLY ASSIT WITH RELEASE | TRUCK AT MOKAMBO BORDER AWAITING CLEARANCE - TO DISPATCH TODAY ONCE RELEASED | TRUCK AT MOKAMBO BORDER STILL WAITING RELEASE | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2559 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | 3F6062292 | CAT00745E3F606229 | TBA | FML2402DSI2399 | COD 2023 314178 | ND436314 | ND646811 / ND644688 | 2402DSI2399 | VESSEL: PIRANHA V. 24PA03 - ETA DURBAN: 13-03-2024 | OFFLOADED | 08-03-2024 | 19-03-2024 | BV COMPLETED | 13-03-2024 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 25-03-2024 | 26-03-2024 | 27-03-2024 | 29-03-2024 | 30-03-2024 | 30-03-2024 | 30-03-2024 | 31-03-2024 | MOKAMBO 31-03-2024 | MOKAMBO 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 04-04-2024 | 06-04-2024 | [6 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | LOADED FROM PORT - AWAITING ESCORTS - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV INSPECTION BOOKED FOR TOMORROW 19-03-2024 | BV INSPECTION BOOKED FOR TODAY, UNITS TO LOAD THIS WEEK ONCE BV IS COMPLETED-AWAITING DISPATCH DATE | TRUCK DISPATCH EN-ROUTE TO BEIRBRIDGE BORDER | TRUCK AT VOLKSRUST EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT POLOKWANE WAITING FOR ESCORT TO PROCEED TO BEIT BRIDGE BORDER | TRUCK AT BEIT BRIDGE ZIM SIDE | TRUCK AT MASVINGO ENROUTE HARARE | TRUCK AT BANKET ENROUTE CHIRUNDU | TRUCK AT MOKAMBO DRC SIDE AWATING RELEASE | TRUCK AT MOKAMBO DRC SIDE AWATING RELEASE | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2561 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | 3F606230 | CAT00745L3F606230 | TBA | FML2402DSI2400 | COD 2023 314178 | BC02MYZM | ND858759 / ND858588 | 2402DSI2400 | VESSEL: PIRANHA V. 24PA03 - ETA DURBAN: 13-03-2024 | OFFLOADED | 08-03-2024 | 19-03-2024 | BV COMPLETED | 13-03-2024 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 23-03-2024 | 25-03-2024 | 26-03-2024 | 27-03-2024 | 30-03-2024 | 30-03-2024 | 30-03-2024 | 31-03-2024 | MOKAMBO 31-03-2024 | MOKAMBO 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 04-04-2024 | 06-04-2024 | [6 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | LOADED FROM PORT - AWAITING ESCORTS - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV INSPECTION BOOKED FOR TOMORROW 19-03-2024 | BV INSPECTION BOOKED FOR TODAY, UNITS TO LOAD THIS WEEK ONCE BV IS COMPLETED-AWAITING DISPATCH DATE | TRUCK DISPATCH EN-ROUTE TO BEIRBRIDGE BORDER | TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT GROBLERSDAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT ENROUTE HARARE | TRUCK AT BANKET ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT MOKAMBO DRC SIDE AWATING RELEASE | TRUCK AT MOKAMBO DRC SIDE AWATING RELEASE | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2562 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | 3F606231 | CAT00745H3F606231 | TBA | FML2402DSI2402 | COD 2023 314178 | BC01ZHN | ND718488 / ND715801 | 2402DSI2401 | VESSEL: PIRANHA V. 24PA03 - ETA DURBAN: 13-03-2024 | OFFLOADED | 08-03-2024 | 19-03-2024 | BV COMPLETED | 13-03-2024 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 23-03-2024 | 25-03-2024 | 26-03-2024 | 27-03-2024 | 30-03-2024 | 30-03-2024 | 30-03-2024 | 31-03-2024 | MOKAMBO 31-03-2024 | MOKAMBO 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 03-04-2024 | 04-04-2024 | 06-04-2024 | [6 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | LOADED FROM PORT - AWAITING ESCORTS - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV INSPECTION BOOKED FOR TOMORROW 19-03-2024 | BV INSPECTION BOOKED FOR TODAY, UNITS TO LOAD THIS WEEK ONCE BV IS COMPLETED-AWAITING DISPATCH DATE | TRUCK DISPATCH EN-ROUTE TO BEIRBRIDGE BORDER | TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT GROBLERSDAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT ENROUTE HARARE | TRUCK AT BANKET ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT MOKAMBO DRC SIDE AWATING RELEASE | TRUCK AT MOKAMBO DRC SIDE AWATING RELEASE | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK AT KOLWELI ENROUTE SITE - TO ARRIVE ON SITE TODAY | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | TRUCK OFFOADED AWAITING SIGNED DELIVERY NOTES | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2625 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01733 | CAT00428KL7D01733 | C4Z14566 | FML2401DSI2372 | COD 2023 297095 | ND834401 | ND854241 | ND64691 | VESSEL: GOLDEN KAROO Voy. 241205 - ETA DURBAN: 14-03-2024 | OFFLOADED 18-04-2024 | 08-03-2024 | 22-03-2024 | BV COMPLETED | 18-03-2024 | 25-03-2024 | MIDDELBURG 26-03-2024 | MIDDELBURG 26-03-2024 | 27-03-2024 | 27-03-2024 | 30-03-2024 | 02-04-2024 | 03-04-2024 | 05-04-2024 | 06-04-2024 | 07-04-2024 | 07-04-2024 | 08-04-2024 | 08-04-2024 | 09-04-2024 | 15-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 18-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IS IN AND WORKING, BV WILL BE BOOKED AS SOON AS UNITS ARE AT OUR FACILITY | TRUCKS IS AT PORT AWAITING TO LOAD, VESSEL STILL WORKING | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | BV ISNPECTION COMPLETED - DISPATCHING DURBAN | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | KADOMA ENROUTE HARARE | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ENROUTE LUSAKA | TRUCK IS AT KASUMBALESA DRC SIDE | TRUCK IS AT WHSIKEY AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 2 AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 3 AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 4 AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 6 AWAITING RELEASE | TRUCK IS AT LUBUMBASHI ENROUTE KOLWEZI | TRUCK IS ON SITE WAITING TO OFFLOAD | TRUCK IS ON SITE WAITING TO OFFLOAD - TO OFFLOAD TODAY | OFFLOADED 18-04-2024 | OFFLOADED 18-04-2024
BA2626 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01734 | CAT00428JL7D01734 | C4Z14565 | FML2401DSI2373 | COD 2023 297095 | ND834401 | ND854241 | ND64691 | VESSEL: GOLDEN KAROO Voy. 241205 - ETA DURBAN: 14-03-2024 | OFFLOADED 18-04-2024 | 08-03-2024 | 22-03-2024 | BV COMPLETED | 18-03-2024 | 25-03-2024 | MIDDELBURG 26-03-2024 | MIDDELBURG 26-03-2024 | 27-03-2024 | 27-03-2024 | 30-03-2024 | 02-04-2024 | 03-04-2024 | 05-04-2024 | 06-04-2024 | 07-04-2024 | 07-04-2024 | 08-04-2024 | 08-04-2024 | 09-04-2024 | 15-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 18-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IS IN AND WORKING, BV WILL BE BOOKED AS SOON AS UNITS ARE AT OUR FACILITY | TRUCKS IS AT PORT AWAITING TO LOAD, VESSEL STILL WORKING | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | BV ISNPECTION COMPLETED - DISPATCHING DURBAN | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | KADOMA ENROUTE HARARE | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ENROUTE LUSAKA | TRUCK IS AT KASUMBALESA DRC SIDE | TRUCK IS AT WHSIKEY AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 2 AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 3 AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 4 AWAITING RELEASE | TRUCK IS AT WHSIKEY DAY 6 AWAITING RELEASE | TRUCK IS AT LUBUMBASHI ENROUTE KOLWEZI | TRUCK IS ON SITE WAITING TO OFFLOAD | TRUCK IS ON SITE WAITING TO OFFLOAD - TO OFFLOAD TODAY | OFFLOADED 18-04-2024 | OFFLOADED 18-04-2024
BA2627 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA |  | L7D01735 | CAT00428CL7D01735 | C4Z14564 | FML2401DSI2374 | COD 2023 297095 | ADS6345 | AAZ0453 | ND64692 | VESSEL: GOLDEN KAROO Voy. 241205 - ETA DURBAN: 14-03-2024 | OFFLOADED 26-04-2024 | 08-03-2024 | 22-03-2024 | BV COMPLETED | 18-03-2024 | 23-03-2024 | 24-03-2024 | 26-07-2024 | 26-07-2024 | 26-07-2024 | 30-03-2024 | 31-03-2024 | 04-04-2024 | 09-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 16-04-2024 | 16-04-2024 | 24-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IS IN AND WORKING, BV WILL BE BOOKED AS SOON AS UNITS ARE AT OUR FACILITY | TRUCKS IS AT PORT AWAITING TO LOAD, VESSEL STILL WORKING | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | BV ISNPECTION COMPLETED - CURRENTLY IN JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | DISPATCHING JOHANNESBURG TODAY FOR BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | HARARE BUSY WITH TRIP CHECK TO DISPATCH ONCE DONE | HARARE BUSY WITH TRIP CHECK TO DISPATCH ONCE DONE - TO DISPATCH LATER TODAY | DISPATCHED HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE, TRUCK TO DISPATCH TODAY | TRUCK TO DISPATCH CHIRUNDU EN-ROUTE TO KASUMBALESA | TRUCKS AT KAFUE EN-ROUTE TO KASUMBALESA BORDER | TRUCKS AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | TRUCKS AT KASUMBALESA ZAM SIDE | TRUCKS AT KASUMBALESA DRC SIDE | TRUCKS AT KASUMBALESA DRC SIDE | TRUCKS AT WHISKEY AWAITING RELEASE | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 4 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 6 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 7 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 8 PLEASE ASSIST | TRUCKS AT KOLWEZI EN-ROUTE TO SITE | TRUCK IS ON SITE WAITING TO OFFLOAD | OFFLOADED 26-04-2024 | OFFLOADED 26-04-2024
BA2628 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01744 | CAT00428CL7D01744 | C4Z14573 | FML2401DSI2375 | COD 2023 297095 | ADS6345 | AAZ0453 | ND64692 | VESSEL: GOLDEN KAROO Voy. 241205 - ETA DURBAN: 14-03-2024 | OFFLOADED 26-04-2024 | 08-03-2024 | 22-03-2024 | BV COMPLETED | 18-03-2024 | 23-03-2024 | 24-03-2024 | 26-07-2024 | 26-07-2024 | 26-07-2024 | 30-03-2024 | 31-03-2024 | 04-04-2024 | 09-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 16-04-2024 | 16-04-2024 | 24-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA 18-03-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IS IN AND WORKING, BV WILL BE BOOKED AS SOON AS UNITS ARE AT OUR FACILITY | TRUCKS IS AT PORT AWAITING TO LOAD, VESSEL STILL WORKING | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON MONDAY THE 25/03/2024 | BV ISNPECTION COMPLETED - CURRENTLY IN JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | DISPATCHING JOHANNESBURG TODAY FOR BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | HARARE BUSY WITH TRIP CHECK TO DISPATCH ONCE DONE | HARARE BUSY WITH TRIP CHECK TO DISPATCH ONCE DONE - TO DISPATCH LATER TODAY | DISPATCHED HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE, TRUCK TO DISPATCH TODAY | TRUCK TO DISPATCH CHIRUNDU EN-ROUTE TO KASUMBALESA | TRUCKS AT KAFUE EN-ROUTE TO KASUMBALESA BORDER | TRUCKS AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | TRUCKS AT KASUMBALESA ZAM SIDE | TRUCKS AT KASUMBALESA DRC SIDE | TRUCKS AT KASUMBALESA DRC SIDE | TRUCKS AT WHISKEY AWAITING RELEASE | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 4 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 6 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 7 PLEASE ASSIST | TRUCKS AT WHISKEY AWAITING RELEASE - DAY 8 PLEASE ASSIST | TRUCKS AT KOLWEZI EN-ROUTE TO SITE | TRUCK IS ON SITE WAITING TO OFFLOAD | OFFLOADED 26-04-2024 | OFFLOADED 26-04-2024
BA2623 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA |  | L7D01731 | CAT00428TL7D01731 | C4Z14567 | FML2402DSI2418 | COD 2023 297095 | ND491242 | ND702944 | ND64699 | VESSEL: BRIGHT SKY Voy. 241206 - ETA DURBAN: 30-03-2024 | OFFLOADED 09-05-2024 | 19-03-2024 | 03-04-2024 | BV COMPLETED | 30-03-2024 | 08-04-2024 | 10-04-2024 | 11-04-2024 | 12-04-2024 | 15-04-2024 | 16-04-2024 | 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 21-04-2024 | 21-04-2024 | 27-04-2024 | 27-04-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 09-05-2024 | [7 empty] | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | VESSEL ARRIVED 30-03-2024 - COLLECTED FROM PORT - BV INSPECTION BOOKED FOR THURSDAY | BV INSPECTION BOOKED FOR TOMORROW 04-04-2024 | BV INSPECTION BOOKED FOR TODAY 04-04-2024 | BV INSPECTION COMPLETED - TO DISPATCH DURBAN | TRUCK TO LOAD AND DISPATCH TODAY THE 08/04/2024 | TRUCK AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | TRUCK AT VOLKSRUST EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT GLOBLERSDAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE ZIM SIDE | RUTENGA ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU | DISPATCHED FROM HARARE ENORUTE CHIRUNDU | CHIRUNDU ZAM SIDE | KASUMBALESA ZAM SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 2 | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 4 | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 5 | KOLWEZI HOLDING YARD | KOLWEZI HOLDING YARD - DAY 2 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 3 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 4 - PLEASE ASSIST | OFFLOADED 09-05-2024 | OFFLOADED 09-05-2024
BA2624 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA |  | L7D01732 | CAT00428PL7D01732 | C4Z14563 | FML2402DSI2419 | COD 2023 297095 | ND491242 | ND702944 | ND64699 | VESSEL: BRIGHT SKY Voy. 241206 - ETA DURBAN: 30-03-2024 | OFFLOADED 09-05-2024 | 19-03-2024 | 03-04-2024 | BV COMPLETED | 30-03-2024 | 08-04-2024 | 10-04-2024 | 11-04-2024 | 12-04-2024 | 15-04-2024 | 16-04-2024 | 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 21-04-2024 | 21-04-2024 | 27-04-2024 | 27-04-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 09-05-2024 | [7 empty] | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | VESSEL ARRIVED 30-03-2024 - COLLECTED FROM PORT - BV INSPECTION BOOKED FOR THURSDAY | BV INSPECTION BOOKED FOR TOMORROW 04-04-2024 | BV INSPECTION BOOKED FOR TODAY 04-04-2024 | BV INSPECTION COMPLETED - TO DISPATCH DURBAN | TRUCK TO LOAD AND DISPATCH TODAY THE 08/04/2024 | TRUCK AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | TRUCK AT VOLKSRUST EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT GLOBLERSDAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE ZIM SIDE | RUTENGA ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU | DISPATCHED FROM HARARE ENORUTE CHIRUNDU | CHIRUNDU ZAM SIDE | KASUMBALESA ZAM SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 2 | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 4 | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 5 | KOLWEZI HOLDING YARD | KOLWEZI HOLDING YARD - DAY 2 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 3 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 4 - PLEASE ASSIST | OFFLOADED 09-05-2024 | OFFLOADED 09-05-2024
BA2630 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01748 | CAT00428JL7D01748 | C4Z14586 | FML2402DSI2420 | COD 2023 297095 | DFM964GP | RNN269GP | ND64700 | VESSEL: BRIGHT SKY Voy. 241206 - ETA DURBAN: 30-03-2024 | OFFLOADED 09-05-2024 | 19-03-2024 | 03-04-2024 | BV COMPLETED | 30-03-2024 | 08-04-2024 | 12-04-2024 | 20-04-2024 | 21-04-2024 | 21-04-2024 | 24-04-2024 | 26-04-2024 | 27-04-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 02-05-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 09-05-2024 | [7 empty] | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | VESSEL ARRIVED 30-03-2024 - COLLECTED FROM PORT - BV INSPECTION BOOKED FOR THURSDAY | BV INSPECTION BOOKED FOR TOMORROW 04-04-2024 | BV INSPECTION BOOKED FOR TODAY 04-04-2024 | BV INSPECTION COMPLETED - TO DISPATCH DURBAN | TRUCK TO LOAD AND DISPATCH TODAY THE 08/04/2024 | TRUCK AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | TRUCK AT HARRISMIRTH EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK TO DISPATCH LATER TODAY | TRUCK DISPATCHING JOHANNESBURG TODAY | VEHICLE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN | VEHICLE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN | VEHICLE ON BREAKDOWN - FINALIZING THIS MORNING - VEHICLE TO DISPATCH THIS AFTERNOON | MUSINA ENROUTE BEIT BRIDGE | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE ZIM SIDE DISPATCHING TODAY | TRUCK AT MASVINGO EN-ROUTE TO CHIRUNDU | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT KASUMBALESA BORDER | VEHICLE AT WHISKEY AWAITING RELEASE | KOLWEZI HOLDING YARD | KOLWEZI HOLDING YARD - DAY 2 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 3 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 4 - PLEASE ASSIST | OFFLOADED 09-05-2024 | OFFLOADED 09-05-2024
BA2633 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | L7D01752 | CAT00428CL7D01752 | C4Z14584 | FML2402DSI2421 | COD 2023 297095 | DFM964GP | RNN269GP | ND64700 | VESSEL: BRIGHT SKY Voy. 241206 - ETA DURBAN: 30-03-2024 | OFFLOADED 09-05-2024 | 19-03-2024 | 03-04-2024 | BV COMPLETED | 30-03-2024 | 08-04-2024 | 12-04-2024 | 20-04-2024 | 21-04-2024 | 21-04-2024 | 24-04-2024 | 26-04-2024 | 27-04-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 02-05-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 09-05-2024 | [7 empty] | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 27-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | AWAITING VESSEL ARRIVAL - ETA 28-03-2024 | VESSEL ARRIVED 30-03-2024 - COLLECTED FROM PORT - BV INSPECTION BOOKED FOR THURSDAY | BV INSPECTION BOOKED FOR TOMORROW 04-04-2024 | BV INSPECTION BOOKED FOR TODAY 04-04-2024 | BV INSPECTION COMPLETED - TO DISPATCH DURBAN | TRUCK TO LOAD AND DISPATCH TODAY THE 08/04/2024 | TRUCK AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | TRUCK AT HARRISMIRTH EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK TO DISPATCH LATER TODAY | TRUCK DISPATCHING JOHANNESBURG TODAY | VEHICLE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN | VEHICLE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN | VEHICLE ON BREAKDOWN - FINALIZING THIS MORNING - VEHICLE TO DISPATCH THIS AFTERNOON | MUSINA ENROUTE BEIT BRIDGE | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE ZIM SIDE DISPATCHING TODAY | TRUCK AT MASVINGO EN-ROUTE TO CHIRUNDU | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT KASUMBALESA BORDER | VEHICLE AT WHISKEY AWAITING RELEASE | KOLWEZI HOLDING YARD | KOLWEZI HOLDING YARD - DAY 2 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 3 - PLEASE ASSIST | KOLWEZI HOLDING YARD - DAY 4 - PLEASE ASSIST | OFFLOADED 09-05-2024 | OFFLOADED 09-05-2024
BA2557 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO50065OX | 3F606227 | CAT00745L3F606227 | TBA | FML2403DSI2465 | COD 2023 314178 | ND437412 | ND647660 | 2404DSI2465 | VESSEL: SILVER RAY V. 24PA03 - ETA DURBAN: 21-03-2024 | OFFLOADED 15-05-2024 | 08-03-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 25-04-2024 | 26-04-2024 | 27-04-2024 | 29-04-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 03-05-2024 | MOKAMBO 04-05-2024 | MOKAMBO 08-05-2024 | 08-05-2024 | 09-05-2024 | 09-05-2024 | 09-05-2024 | 10-05-2024 | 15-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA 16-04-2024 | AWAITING VESSEL ARRIVAL - ETA 16-04-2024 | AWAITING VESSEL ARRIVAL - ETA 16-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ARRIVAL MOVED OUT - NEW ETA 21-04-2024 | AWAITING VESSEL ARRIVAL - ARRIVAL MOVED OUT - NEW ETA 21-04-2024 | AWAITING VESSEL ARRIVAL - ARRIVAL MOVED OUT - NEW ETA 21-04-2024 | VESSEL ARRIVED YESTERDAY - LOADING FROM PORT TODAY / TOMORROW | BV INSPECTION IS BOOKED FOR TUESDAY 23-04-2024 | BV INSPECTION IS BOOKED FOR TUESDAY 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, UNITS TO DISPATCH THE 24/04/2024 | TRUCKS ARE AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | TRUCKS ARE AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | VEHICLE PASSING HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE MAKOMBO BORDER | KITWE ENROUTE MAKOMBO BORDER | MOKAMBO BORDER AWAITING RELEASE | MOKAMBO BORDER AWAITING RELEASE - DAY 5 | MOKAMBO BORDER AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE | PASSING FUNGURUME ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 15-05-2024 | OFFLOADED 15-05-2024
BA2558 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO50065OX | 3F606228 | CAT00745H3F606228 | TBA | FML2403DSI2466 | COD 2023 314178 | ND431993 | ND923084 | 2403DSI2466 | VESSEL: SILVER RAY V. 24PA03 - ETA DURBAN: 21-03-2024 | OFFLOADED 15-05-2024 | 08-03-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 25-04-2024 | 30-04-2024 | 01-05-2024 | 01-05-2024 | 04-05-2024 | 04-05-2024 | 04-05-2024 | 04-05-2024 | MOKAMBO 05-05-2024 | MOKAMBO 08-05-2024 | 08-05-2024 | 09-05-2024 | 09-05-2024 | 09-05-2024 | 10-05-2024 | 15-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA 16-04-2024 | AWAITING VESSEL ARRIVAL - ETA 16-04-2024 | AWAITING VESSEL ARRIVAL - ETA 16-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ETA 17-04-2024 | AWAITING VESSEL ARRIVAL - ARRIVAL MOVED OUT - NEW ETA 21-04-2024 | AWAITING VESSEL ARRIVAL - ARRIVAL MOVED OUT - NEW ETA 21-04-2024 | AWAITING VESSEL ARRIVAL - ARRIVAL MOVED OUT - NEW ETA 21-04-2024 | VESSEL ARRIVED YESTERDAY - LOADING FROM PORT TODAY / TOMORROW | BV INSPECTION IS BOOKED FOR TUESDAY 23-04-2024 | BV INSPECTION IS BOOKED FOR TUESDAY 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, UNITS TO DISPATCH THE 24/04/2024 | TRUCKS ARE AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | TRUCKS ARE AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | PASSING MASVINGO ENROUTE HARARE | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER TO DISPATCH TODAY | MOKAMBO BORDER AWAITING RELEASE | MOKAMBO BORDER AWAITING RELEASE - DAY 3 | MOKAMBO BORDER AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE | PASSING FUNGURUME ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 15-05-2024 | OFFLOADED 15-05-2024
BA2650 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01775 | CAT00428CL7D01775 | TBA | FML2403DSI2446 | COD 2023 314178 | TBA | TBA | ND64722 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 16-05-2024 | 04-04-2024 | 29-04-2024 | BV COMPLETED | 17-04-2024 | 27-04-2024 | 28-04-2024 | 29-04-2024 | 30-04-2024 | 30-04-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 06-05-2024 | 07-05-2024 | 07-05-2024 | 08-05-2024 | 13-05-2024 | 13-05-2024 | 15-05-2024 | 15-05-2024 | 15-05-2024 | 16-05-2024 | 15-06-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | PLANNING TO LOAD AND DISPATCH THE TRUCK ON THE 30/04/2024-TRUCK ONDERGOING TRIP CHECK AND REGISTRATION | PLANNING TO LOAD AND DISPATCH THE TRUCK ON THE 30/04/2024-TRUCK ONDERGOING TRIP CHECK AND REGISTRATION | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | VEHICLE IN JOHANNESBURG ENROUTE BEIT BRIDGE | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT BEIT BRIDGE ZIM SIDE | VEHICLE AT BEIT BRIDGE ZIM SIDE | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN | KASUMBALESA ZAM SIDE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN - WAITING NEW PART TO ARRIVE TODAY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 16-05-2024 | OFFLOADED 16-05-2024
BA2651 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO49892OX | L7D01774 | CAT00428EL7D01774 | TBA | FML2403DSI2447 | COD 2024 165868 | TBA | TBA | ND64722 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 16-05-2024 | 10-04-2024 | 29-04-2024 | BV COMPLETED | 17-04-2024 | 27-04-2024 | 28-04-2024 | 29-04-2024 | 30-04-2024 | 30-04-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 06-05-2024 | 07-05-2024 | 07-05-2024 | 08-05-2024 | 13-05-2024 | 13-05-2024 | 15-05-2024 | 15-05-2024 | 15-05-2024 | 16-05-2024 | 15-06-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | PLANNING TO LOAD AND DISPATCH THE TRUCK ON THE 30/04/2024-TRUCK ONDERGOING TRIP CHECK AND REGISTRATION | PLANNING TO LOAD AND DISPATCH THE TRUCK ON THE 30/04/2024-TRUCK ONDERGOING TRIP CHECK AND REGISTRATION | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | VEHICLE IN JOHANNESBURG ENROUTE BEIT BRIDGE | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT BEIT BRIDGE ZIM SIDE | VEHICLE AT BEIT BRIDGE ZIM SIDE | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN | KASUMBALESA ZAM SIDE ON BREAKDOWN - ATTENDING TO THE BREAKDOWN - WAITING NEW PART TO ARRIVE TODAY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 16-05-2024 | OFFLOADED 16-05-2024
BA2644 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01766 | CAT00428CL7D01766 | TBA | FML2403DSI2440 | COD 2023 314178 | JV80FPGP | JZ68SNGP | NC64725 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 24-05-2024 | 04-04-2024 | 29-04-2024 | BV COMPLETED | 17-04-2024 | 27-04-2024 | 28-04-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 02-05-2024 | 05-05-2024 | 10-05-2024 | 10-05-2024 | 11-05-2024 | 12-05-2024 | 12-05-2024 | 13-05-2024 | 13-05-2024 | 18-05-2024 | 18-05-2024 | 19-05-2024 | 20-05-2024 | 24-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | VEHICLE IN JOHANNESBURG ENROUTE BEIT BRIDGE | VEHICLE IN JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATHING FOR THE BORDER | VEHICLE AT BEIT BRIDGE ZIM SIDE | VEHICLE AT HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATHING CHIRUNDU | CHIRUNDU AWAITING RELEASE | KASUMBALESA ZAM SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 24-05-2024
BA2645 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01767 | CAT00428VLD01767 | TBA | FML2403DSI2441 | COD 2023 314178 | JV80FPGP | JZ68SNGP | NC64725 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 24-05-2024 | 04-04-2024 | 29-04-2024 | BV COMPLETED | 17-04-2024 | 27-04-2024 | 28-04-2024 | 01-05-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 02-05-2024 | 05-05-2024 | 10-05-2024 | 10-05-2024 | 11-05-2024 | 12-05-2024 | 12-05-2024 | 13-05-2024 | 13-05-2024 | 18-05-2024 | 18-05-2024 | 19-05-2024 | 20-05-2024 | 24-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | TRUCK TO LOAD AND DISPATCH ON THE 27/04/2024 | VEHICLE IN JOHANNESBURG ENROUTE BEIT BRIDGE | VEHICLE IN JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATHING FOR THE BORDER | VEHICLE AT BEIT BRIDGE ZIM SIDE | VEHICLE AT HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATHING CHIRUNDU | CHIRUNDU AWAITING RELEASE | KASUMBALESA ZAM SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 24-05-2024
BA2646 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01769 | CAT00428LL7D01769 | TBA | FML2403DSI2442 | COD 2023 314178 | CB67PGGP | KH82PCGP | ND64724 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 24-05-2024 | 04-04-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 28-04-2024 | 28-04-2024 | 30-04-2024 | 02-05-2024 | 05-05-2024 | 06-05-2024 | 06-05-2024 | 07-05-2024 | 07-05-2024 | 08-05-2024 | 11-05-2024 | 11-05-2024 | 15-05-2024 | 16-05-2024 | 18-05-2024 | 18-05-2024 | 24-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT MASVINGO ENROUTE HARARE | VEHICLE AT HARARE | VEHICLE DISPATCHING HARARE | CHIRUNDU ZIM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE KOLWEZI | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 24-05-2024
BA2647 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01770 | CAT00428VLD01770 | TBA | FML2403DSI2443 | COD 2023 314178 | CB67PGGP | KH82PCGP | ND64724 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 24-05-2024 | 04-04-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 28-04-2024 | 28-04-2024 | 30-04-2024 | 02-05-2024 | 05-05-2024 | 06-05-2024 | 06-05-2024 | 07-05-2024 | 07-05-2024 | 08-05-2024 | 11-05-2024 | 11-05-2024 | 15-05-2024 | 16-05-2024 | 18-05-2024 | 18-05-2024 | 24-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT MASVINGO ENROUTE HARARE | VEHICLE AT HARARE | VEHICLE DISPATCHING HARARE | CHIRUNDU ZIM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE KOLWEZI | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 24-05-2024
BA2648 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01773 | CAT00428HL7D01773 | TBA | FML2403DSI2444 | COD 2023 314178 | JN38KXGP | XVD958GP | ND64723 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 24-05-2024 | 04-04-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 28-04-2024 | 28-04-2024 | 30-04-2024 | 02-05-2024 | 02-05-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 05-05-2024 | 06-05-2024 | 09-05-2024 | 09-05-2024 | 15-05-2024 | 16-05-2024 | 16-05-2024 | 17-05-2024 | 24-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT MWENEZI ENROUTE HARARE | VEHICLE AT HARARE | VEHICLE AT CHIRUNDU ZAM SIDE | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE TO CROSS TO DRC | KASUMBALESA ZAM SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | ON SITE WAITING TO OFFLOAD - DAY 6 | ON SITE WAITING TO OFFLOAD - DAY 7 | ON SITE WAITING TO OFFLOAD - DAY 8 | OFFLOADED 24-05-2024
BA2649 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50065OX | L7D01772 | CAT00428LL7D01772 | TBA | FML2403DSI2445 | COD 2023 314178 | JN38KXGP | XVD958GP | ND64723 | VESSEL: GREY FOX Voy. 241207 - ETA DURBAN: 17-04-2024 | OFFLOADED 24-05-2024 | 04-04-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 28-04-2024 | 28-04-2024 | 30-04-2024 | 02-05-2024 | 02-05-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 05-05-2024 | 06-05-2024 | 09-05-2024 | 09-05-2024 | 15-05-2024 | 16-05-2024 | 16-05-2024 | 17-05-2024 | 24-05-2024 | [36 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL- VESSEL MOVED OUT - NEW ETA DURBAN 18-04-2024 | VESSEL ARRIVED YESTERDAY - BUSY DISCHARGING CARGO | VESSEL BUSY DISCHARGING CARGO - VEHICLE ON STANDBY TO LOAD - BV INSPECTION BOOKED FOR TUESDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION IS BOOKED FOR TODAY, AWAITING DISPATCH DATE | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK BEFORE DISPATCH | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT MWENEZI ENROUTE HARARE | VEHICLE AT HARARE | VEHICLE AT CHIRUNDU ZAM SIDE | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE TO CROSS TO DRC | KASUMBALESA ZAM SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | ON SITE WAITING TO OFFLOAD - DAY 6 | ON SITE WAITING TO OFFLOAD - DAY 7 | ON SITE WAITING TO OFFLOAD - DAY 8 | OFFLOADED 24-05-2024
BA2652 | CAT UG20 MINING GRADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | TBA | 20WN0126 | CAT0120KPSZN20399 | TBA | FML2402DSI2422 | COD 2023 297095 PT20 | BCF1075ZM | BCF6192ZM | 2402DSI2422 | VESSEL: GSL MELITA V. 407N - Transhipment Vessel: APL HOUSTON Voy. 410S - ETA DURBAN: 27-04-2024 | OFFLOADED 10-06-2024 | 12-04-2024 | 20-05-2024 | BV COMPLETED | 27-04-2024 | 22-05-2024 | 22-05-2024 | 22-05-2024 | 22-05-2024 | GROBLERS BRIDGE BORDER 23-05-2024 | GROBLERS BRIDGE BORDER 25-05-2024 | FRANCISTOWN 25-05-2024 | KAZUNGULA BW 25-05-2024 | KAZUNGULA ZM 26-05-2024 | 27-05-2024 | 27-05-2024 | 30-05-2024 | 01-06-2024 | 03-06-2024 | 03-06-2024 | 05-06-2024 | 05-06-2024 | 06-06-2024 | 06-06-2024 | 10-06-2024 | [8 empty] | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 13-04-2024 | AWAITING VESSEL ARRIVAL - ETA 22-04-2024 | AWAITING VESSEL ARRIVAL - ETA 22-04-2024 | AWAITING VESSEL ARRIVAL - ETA 22-04-2024 | AWAITING VESSEL ARRIVAL - ETA 22-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 23-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 26-04-2024 | AWAITING VESSEL ARRIVAL - ETA 27-04-2024 | VESSEL IN AND WORKING | LOADED - AWAITING CONFIRMATION OF BV INSPECTION DATE FROM BV RSA | LOADED - BV INSPECTION BOOKED FOR TUESDAY 07-05-2024 FIRST AVAILABLE INSPECTION DATE | BV INSPECTION DATE TO BE CONFIRMED | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION DATE TO BE CONFIRMED - ISSUE WITH BV LICNESE | BV INSPECTION BOOKED FOR MONDAY 20-05-2024 | BV INSPECTION BOOKED FOR TODAY 20-05-2024 | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN TODAY | GROBLERSBRUG CLEARING | GROBLERSBRUG CLEARING | LUSAKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE CHECK | NDOLA UNDER ROUTINE MAINTENANCE CHECK | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TUMBWE ENROUTE KOLWEZI | ON SITE WAITING RELEASE AND OFFLOADING | ON SITE WAITING RELEASE AND OFFLOADING - DAY 5 | OFFLOADED 10-06-2024 | OFFLOADED 10-06-2024
BA2665 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 50846OX | L7D01736 | CAT00428VL7D01736 | C4Z14575 | FML2401DSI2376 | COD 2024186357 | BCC5806 ZM | BCE 3681 ZM | 2401DSI2376 | VESSEL: GOLDEN KAROO Voy. 241205 - ETA DURBAN: 16-03-2024 | OFFLOADED 20-06-2024 | 10-05-2024 | 15-05-2024 | BV COMPLETED | 16-03-2024 | 17-05-2024 | 18-05-2024 | 18-05-2024 | 18-05-2024 | GROBLERS BRIDGE BORDER 18-05-2024 | GROBLERS BRIDGE BORDER 20-05-2024 | FRANCISTOWN 21-05-2024 | KAZUNGULA BW 21-05-2024 | KAZUNGULA ZM 28-05-2024 | 29-05-2024 | 30-05-2024 | 03-06-2024 | 06-06-2024 | 12-06-2024 | 13-06-2024 | 15-06-2024 | 15-06-2024 | 16-06-2024 | 17-06-2024 | 20-06-2024 | [58 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING VALIDATION OF BV NUMBER - INSPECTION DATE TO BE CONFIRMED ONCE THE LICENSE IS VALIDATED | AWAITING VALIDATION OF BV NUMBER - INSPECTION DATE TO BE CONFIRMED ONCE THE LICENSE IS VALIDATED | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING TODAY | LOADED - DISPATCHING DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA | KAZUNGULA ZAM SIDE CLEARING | KAZUNGULA ZAM SIDE CLEARING | KAZUNGULA ZAM SIDE CLEARING | KAZUNGULA ZAM SIDE AWAITING RELEASE | KAZUNGULA ZAM SIDE - VEHICLE ON BREAKDOWN - MECHANIC ATTENDING TO THE VEHICLE | KABWE ENROUTE NDOLA | KAPIRI MPOSHI ENROUTE NDOLA | NDOLA UNDER ROUTINE CHECKS | CHILILABOMBWE ENROUTE KASUMBALESA | CHILILABOMBWE AWAITING DOCUMENTS TO BE RELEASE TO PROCEED TO KASUMBALESA | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER AWAITING RELEASE - DAY 5 | KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 20-06-2024
BA2769 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 52189 OX | DXZ04073 | CAT0226BCDXZ04073 | CZ212465 | FML2409DSI2586 | COD 2024 288129 | AJB9958 | N/A | 2409DSI2586 | VESSEL: MSC ALIZEE III Voy. SI436R - TRANSHIPMENT VESSEL: MSC BRASILIA VII V. ZF440R ETA DURBAN: 03-11-2024 | OFFLOADED 18-12-2024 | 08-11-2024 | 11-11-2024 | BV COMPLETE | 03-11-2024 | 19-11-2024 | 20-11-2024 | 21-11-2024 | 21-11-2024 | GRB 21-11-2024 | GRB 24-11-2024 | FRANCISTOWN 24-11-2024 | KAZUNGULA 24-11-2024 | KAZUNGULA 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | MOKAMBO BORDER 30-11-2024 | MOKAMBO BORDER 06-12-2024 | 07-12-2024 | 10-12-2024 | 11-12-2024 | 11-12-2024 | 12-12-2024 | 18-12-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 01-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 01-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 03-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 03-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 03-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - AWAITING DISCHARGE OF CONTAINER | COLLECTING CONTAINER FROM PORT TODAY | UNIT AT BONDED FACILITY - AWAITING AMENDMENTS ON BV LICENSE | BV INSPECITON TO BE DONE MONDAY OR TUESDAY | BV INSPECITON TO BE DONE TODAY | BV INSPECTION COMPLETED - LOADING THURSDAY | BV INSPECTION COMPLETED - LOADING FRIDAY | BV INSPECTION COMPLETED - LOADING FRIDAY | LOADING DELAY - VEHICLE ENROUTE DURBAN - LOADING NEXT WEEK | LOADING TOMORROW 19-11-2024 | LOADING TODAY | ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERSBRIDGE BORDER | GROBERLSBRIDGE BORDER CLEARING | KAZUNGULA BORDER ON THE BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ON THE ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ON THE ZAMBIAN SIDE AWAITING RELEASE | LIVINGSTONE ENROUTE KASUMBALESA BORDER | MONZE ENOUTE DRC BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CROSSING TO DRC SIDE | MOKAMBO BORDER DRC SIDE - TO DISPATCH FOR WHISKEY | DISPATCHED MOKAMBO ENROUTE KASUMBALESA / WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING CUSTOMS STAMP TO EXIT WHISKEY | KANYAKA AWAITING RELEASE | KOLWEZI ENROUTE SITE | KAKULA SITE WAITING TO OFFLOAD | KAKULA SITE WAITING TO OFFLOAD - DAY 5 | KAKULA SITE WAITING TO OFFLOAD - DAY 6 | KAKULA SITE WAITING TO OFFLOAD - DAY 7 | OFFLOADED 18-12-2024
BA2770 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOA COPPER SA | PO 52189 OX | DXZ04074 | CAT0226BVDXZ04074 | CZ212451 | FML2409DSI2586 | COD 2024 288114 | AJB9958 | N/A | 2409DSI2586 | VESSEL: MSC ALIZEE III Voy. SI436R - TRANSHIPMENT VESSEL: MSC BRASILIA VII V. ZF440R ETA DURBAN: 03-11-2024 | OFFLOADED 18-12-2024 | 23-09-2024 | 11-11-2024 | BV COMPLETE | 03-11-2024 | 19-11-2024 | 20-11-2024 | 21-11-2024 | 21-11-2024 | GRB 21-11-2024 | GRB 24-11-2024 | FRANCISTOWN 24-11-2024 | KAZUNGULA 24-11-2024 | KAZUNGULA 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | MOKAMBO BORDER 30-11-2024 | MOKAMBO BORDER 06-12-2024 | 07-12-2024 | 10-12-2024 | 11-12-2024 | 11-12-2024 | 12-12-2024 | 18-12-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-09-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 19-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 22-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 25-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 30-10-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 01-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 01-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 03-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 03-11-2024 | AWAITING VESSEL ARRIVAL - NEW ETA DURBAN: 03-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - AWAITING DISCHARGE OF CONTAINER | COLLECTING CONTAINER FROM PORT TODAY | UNIT AT BONDED FACILITY - AWAITING AMENDMENTS ON BV LICENSE | BV INSPECITON TO BE DONE MONDAY OR TUESDAY | BV INSPECITON TO BE DONE TODAY | BV INSPECTION COMPLETED - LOADING THURSDAY | BV INSPECTION COMPLETED - LOADING FRIDAY | BV INSPECTION COMPLETED - LOADING FRIDAY | LOADING DELAY - VEHICLE ENROUTE DURBAN - LOADING NEXT WEEK | LOADING TOMORROW 19-11-2024 | LOADING TODAY | ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERSBRIDGE BORDER | GROBERLSBRIDGE BORDER CLEARING | KAZUNGULA BORDER ON THE BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ON THE ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ON THE ZAMBIAN SIDE AWAITING RELEASE | LIVINGSTONE ENROUTE KASUMBALESA BORDER | MONZE ENOUTE DRC BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CROSSING TO DRC SIDE | MOKAMBO BORDER DRC SIDE - TO DISPATCH FOR WHISKEY | DISPATCHED MOKAMBO ENROUTE KASUMBALESA / WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING CUSTOMS STAMP TO EXIT WHISKEY | KANYAKA AWAITING RELEASE | KOLWEZI ENROUTE SITE | KAKULA SITE WAITING TO OFFLOAD | KAKULA SITE WAITING TO OFFLOAD - DAY 5 | KAKULA SITE WAITING TO OFFLOAD - DAY 6 | KAKULA SITE WAITING TO OFFLOAD - DAY 7 | OFFLOADED 18-12-2024

## TRANSIT SUMMARY (hidden)
CLIENT PO | CARGO DETAILS | DBN ARR | DBN DISP | DELIVERED | WAITING DAYS FROM VESSEL ARRIVAL TO ACTUAL DISPATCH | WAITING BV | WAITING DAYS - TRANSIT CEARANCE | TOTAL TRANSIT | WAITING DAYS TO OFFLOAD | ACTUAL TRANSIT DAYS | COMMENTS