## Sheet1
FML
Load Desc. | CAT 6060 FRAME (RH) | CAT 6060 FRAME (LH) | CAT 6060 CAR BODY | CAT 6060 CHASSIS | CAT 6060 MODULE AR POWER | CAT 6060 RISER,COOLER,CABIN,HYDRAULICS | CAT 6060 COUNTERWEIGHT LOWER | CAT 6060 BOOM | CAT 6060 STICK | CAT 6060 COUNTERWEIGHT UPPER
FROM | DURBAN | DURBAN | DURBAN | DURBAN | DURBAN | DURBAN | DURBAN | DURBAN | DURBAN | DURBAN
TO | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG | MIDDELBURG
TO | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI | KOLWEZI
Driver | COLLEN | TAURAYI | THABISO | LAWRENCE | AARON | LIVINGSTON | OXLAND | THULANI | FRANS | LOVEMORE
Fleet | F23 | F17 | F31 | F38 | F18 | F21 | F34 | F39 | F33
Truck | FV44CKGP | B951BRN | KP92RMGP | MP78HBGP | BT14FTGP | CP46TLGP | BT33PGZN | LH95JBGP | BT33NKZN | AGJ9934
Dolly | HK14FMGP | B967BRN | XVL628GP | ZGN692GP | KN31XHGP
Trailer | HK31PVGP | B966BRN | XXZ257GP | ZGN698GP | KN31WVGP | JL05LYGP | YZS906GP | LD49LSGP | KW72PLGP | AFQ8785
Date
2026-05-26 | Waiting to load | Waiting to load | Waiting to load | Waiting to load | Waiting to load | Loaded-Awaiting permit | Catoridge-En route | Loaded-Awaiting police escorts | Catoridge-En route | Loaded-En route
2026-05-27 | Catoridge | PMB Weighbridge-Waiting to weigh and issue permit (Foreign truck) | Port-Loaded-Will start off today | Waiting to load | Waiting to load | Port-Starting off today | Volksrust-Awaiting MP permit | PMB-Awaiting police through town | Van Reenens | Van Reenens
2026-05-28 | Amersfoort | Ladysmith | PMB-Awaiting police through town | Loaded-Awaiting BV inspection | Catoridge | Greytown | Amersfoort | Greytown | Villiers | Van Reenens-Awaiting FS permit
2026-05-29 | Roedtan | Middelburg | Weenen | Greytown-Awaiting police through town | Catoridge | Volksrust | Roedtan | Van Reenens | JHB | Heidelberg
2026-06-01 | BBR-SA side | Musina | Van Reenens | Van Reenens | Catoridge-Departing today | Sasol Doornkop | BBR-SA side | Harrismith | FKT Yard-Major service-Should leave by Wednesday | FKT Yard-General checks
2026-06-02 | BBR-ZIM side | BBR-ZIM side | Van Reenens-Awaiting FS permit | Van Reenens-Awaiting FS permit | Greytown | Roedtan | BBR-ZIM side | Harrismith-Impounded-Width incorrect on PL-Awaiting amended permit | FKT Yard-Major service-Should leave by Wednesday | FKT Yard-General checks
2026-06-03 | Gweru | Gweru | JHB | Villiers | Van reenens | Mogwadi | Gweru | Harrismith-Impounded-Width incorrect on PL-Awaiting amended permit | PTA | PTA
2026-06-04 | Hurungwe | Hurungwe | Polokwane | FKT Yard-General checks | FKT Yard-General checks | Musina-Breakdown-Attending asap | Hurungwe | JHB | BBR-Zim side-Awating release | Musina
2026-06-05 | Chirundu-Zim side | Chirundu-Zim side | Musina | FKT Yard-General checks | Polokwane | BBR-Zim side | Chirundu-Zim side | FKT Yard-General checks | Chivi | BBR-Zim side
2026-06-08 | Chirundu-Zam side-En route | Chirundu-Zam side-En route | Harare | FKT-En route | BBR-SA side | Chirundu-Zam side-En route | Chirundu-Zam side-En route | FKT-Awaiting police-ETA 9am | Chirundu-Zam side-En route | Chirundu-Zim side
2026-06-09 | Kabwe | Kabwe | Chirundu-Zim side | BBR-SA Side | Nvungu | Lusaka | Kabwe | Roedtan | Kabwe | Chirundu-Zam side
2026-06-10 | Chingola | Chingola | Chirundu-Zam side-Awaiting release | Nvungu | Mapinga | Kapiri | Chingola | Polokwane | Chingola | Ndola
2026-06-11 | Queue to Kasumbalesa | Queue to Kasumbalesa | Chirundu-Zam side-Awaiting release | Harare | Chirundu-Zim side | Chililabombwe | Queue to Kasumbalesa | Venitia mine-Awaiting police | Queue to Kasumbalesa | Queue to Kasumbalesa
2026-06-12 | Kasumbalesa-DRC side | Kasumbalesa-DRC side | Lusaka | Hurungwe | Chirundu-Zam side | Kasumbalesa-Zam side | Kasumbalesa-DRC side | BBR-SA side | Kasumbalesa-DRC side | Queue to Kasumbalesa
2026-06-13 | En Route to Wisky | En Route to Wisky | Chisamba | Chirundu-Zim side | Chisamba | En Route to Wisky | En Route to Wisky | BBrR-Zim side | En Route to Wisky | Queue to Kasumbalesa
2026-06-14 | Whisky | Whisky | Kitwe | Chirundu-Zam side | Kitwe | Whisky | Whisky | Harare | Whisky | Whisky
2026-06-15 | Whisky | Whisky | 3km to Kasumbalesa | Chisamba | 3km to Kasumbalesa | Whisky | Whisky | Chirundu-Zim side | Whisky | Wisky